## Dashboard
VINLAND
Development dashboard · one page for scope, time, and cost
Working title | Vinland |  | PHASE COST
Production start | 2026-11-02 |  | Phase | Weeks | Labor | Share
Total weeks | 52 |  | Preproduction | 8 | 30600 | 9.471%
Target ship | 2027-10-31 |  | Vertical slice | 10 | 63600 | 19.68%
Labor cost | 323100 |  | Production | 18 | 118800 | 36.77%
Fully loaded cost | 460504.8 |  | Alpha | 6 | 46400 | 14.36%
Backlog items | 65 |  | Beta | 6 | 39100 | 12.1%
Must-ship items | 54 |  | Polish and ship | 4 | 24600 | 7.614%
Break-even units | 44085 |  | Total | 52 | 323100 | 100%
WHAT THE GAME IS
Oregon Trail structure on the Karlsefni voyage. Leave Greenland in a knarr with a hold that is already full. Keep latitude with a star ring and a sun board. Fish, hunt, forage, and build with the same gamepad grammar. Winter a camp. Trade milk and red cloth until fear caps. Send timber home. Bring a second ship back. A qualified win is the saga ending: leave rich. A full win is a manned camp that has sent two cargoes and received one relief ship.
FIVE VERBS · NOTHING IS A SIDE ACTIVITY
Verb | Mini-game |  | Pays the hold
Navigate | Ring and sun board |  | Refunds drift, saves food
Fish | Line and net |  | Meals, then a food unit if dried
Hunt | One-shot stalk |  | Meat, hides, a possible fear tick
Forage | Measured take |  | Calories now, or a patch next season
Build | Joint and lift |  | Byre, rack, slipway, the return itself
SCOPE GATE
Cut order if the vertical slice slips: Hóp second site, sealing, the Thorhall split, then the third summer. Never cut the star ring, the hold, the byre, the fear clock, or the return cargo. Those five are the game.
HEALTH CHECKS · READ AT EVERY GATE
Check | Value | Target | Status | Source
Backlog load, all owners | 39.66% | 60% or less | OK | Backlog capacity check
Most loaded owner | Design · 83% | 80% or less | Over | Backlog capacity check
Spare hold at departure (units) | 0 | 0 to 1: full but legal | OK | HoldCheck
Timber units that fit going home | 17 | >= 4 | OK | HoldCheck
Planned crossing days | 13 | Info | Info | HoldCheck
Net per unit sold | 10.446 | Info | Info | Breakeven
Units to recover cash outlay | 9443 | Info | Info | Breakeven
Highest risk score | 16 | Below 15 | Act | Risks
Top risk | Store page goes up too late to build wishlists | Owner acting on it | Info | Risks
Risks scored 12+ not closed | 9 | 0 by Beta | Tight | Risks
Backlog items done | 7 of 65 | Tracks the phase | Info | Backlog status
Must-ship days done | 16.99% | 100% at G3 | Info | Backlog status
Gates passed | 2 of 6 | One per phase | Info | Milestones status

## Assumptions
VINLAND
Assumptions · edit the yellow cells; every other sheet recalculates from here
PROJECT
Working title | Vinland
Studio / lead | Independent · Nick Doney Sr. (nickdoneysr)
Plan date | 2026-10-09 | Revised 16 Oct 2026
Production start | 2026-11-02 | Every date in the workbook flows from this cell
Target platform | PC, gamepad-first | Steam Deck Verified is the stretch target
Engine assumption | Godot 4.3, 2D painted | Decided 17 Oct 2026: one project exports PC (Steam) and HTML5 (itch.io)
Build scope | Single-player, 6 to 8 hours | One run is three summers, roughly three evenings
Currency | USD
PHASE LENGTHS (WEEKS)
Phase | Weeks | Notes
Preproduction | 8 | Pillar lock, paper prototype of the ring and the hold, vertical-slice scope
Vertical slice | 10 | One sea leg, star ring, line fishing, one camp day, one joint
Production | 18 | All legs, all five verbs, settlement year, trade, return voyage
Alpha | 6 | Feature complete, economy pass, first full three-summer run
Beta | 6 | Difficulty, haptics, accessibility, content lock
Polish and ship | 4 | Store page, trailer, day-one patch buffer
Total weeks · target ship | 52 | 2027-10-31
RATES AND OVERHEAD
Item | Value | Unit / note
Design week rate | 1800 | USD per person-week, blended
Engineering week rate | 2200 | USD per person-week, blended
Art week rate | 1700 | USD per person-week, blended
Audio week rate | 1600 | USD per person-week, contractor
QA week rate | 1200 | USD per person-week
Production week rate | 1900 | USD per person-week
Overhead on labor | 15% | Tools, engine seats, cloud builds
Contingency | 12% | Applied after overhead
Outsource art budget | 18000 | USD, ships, UI frames, sky plates
Music and foley budget | 12000 | USD, beyond staff audio weeks
Store, trailer, legal | 4000 | USD
Playtest honoraria | 2500 | USD
ECONOMY TUNING KNOBS (DESIGN INPUTS)
Knob | Value | Used by
Knarr cargo units | 24 | Hull model
Party size, default | 24 | Starting load
Food unit feeds (people x days) | 168 | 12 people x 14 days
Drink unit covers (people x days) | 120 | 12 people x 10 days
Good day's sail (nm) | 120 | Six watches
Open-water leg (nm) | 400 | Labrador Sea
Full game length (summers) | 3 | Win condition window
Winters to survive | 2 | Colony clock
Timber units to open a return | 4 | Route unlock
Fear cap (trade breaks) | 5 | Skrælingar clock
HOLD LOADING KNOBS (FEED THE HOLDCHECK SHEET)
Knob | Value | Used by
Cargo units per person | 0.4 | HoldCheck · same rule as Systems "Cargo hold"
Cargo units per head of cattle | 1.5 | HoldCheck · a bull counts as cattle
Cargo units per sheep or goat | 0.4 | HoldCheck
Cattle at departure (bull included) | 2 | Default load. The bull is a trade good and a risk
Sheep and goats at departure | 6 | Default load
Fodder unit covers (cattle-days) | 40 | Animal ration at sea
Sheep fodder as share of a cow | 0.25 | A sheep eats a quarter of a cow
Trade goods carried (units) | 2 | Red cloth and iron
Outbound route distance (nm) | 1200 | Design estimate: Eriksfjord to the Strait via Helluland and Markland
Weather and lost-day factor | 1.3 | Multiplies clean sailing days
Crew sailing the return | 10 | The rest winter the camp
Cargo units per timber unit | 1 | Return cargo
RELEASE AND REVENUE (FEEDS BREAKEVEN)
Item | Value | Unit / note
List price | 19.99 | USD, premium single purchase (Release: price stance)
Realized price factor | 80% | Planning assumption: launch discount, regional pricing, sales-tax netting
Refund rate | 8% | Planning assumption
Steam revenue share | 30% | Steam standard tier (first $10M gross per title)
itch.io revenue share | 10% | itch.io default under open revenue sharing; the creator can change it
Share of units sold on itch.io | 5% | Planning assumption; Steam is the primary store
Steam Direct fee | 100 | USD per app, recoupable once the app earns $1,000 gross
Cultural and historical consultant | 3000 | USD, sensitivity read of the market, visitors, and saga text (Risk R11)
Sales scenario 1 (units) | 2000 | Breakeven scenario table
Sales scenario 2 (units) | 5000 | Breakeven scenario table
Sales scenario 3 (units) | 10000 | Breakeven scenario table
Sales scenario 4 (units) | 25000 | Breakeven scenario table
Sales scenario 5 (units) | 50000 | Breakeven scenario table
HOW TO READ THIS WORKBOOK
Yellow cells with blue text are the only inputs. Change a rate or a phase length and the budget and the ship date move.
Green text is a value pulled from another sheet. Black text is a formula on this sheet.
Dashboard is the one-page read, with health checks at the bottom. Schedule owns dates. TeamBudget owns cost. Backlog owns scope. Breakeven owns revenue.
Mini-games and Systems are the design contract the backlog implements. Do not cut a verb without cutting its backlog rows.
HoldCheck proves the default departure load fits the knarr and that four timber units fit going home. Tune the hold knobs above, not the sheet.
Timeline draws the Schedule week by week. Add weeks on this sheet and the bars move.
Status columns on Backlog, Milestones, and Risks are the only inputs outside this sheet. The Dashboard health checks read them.
Revenue figures are planning assumptions, not forecasts. Store shares are the published defaults; check them again before launch.
Historical spine: Karlsefni's colony attempt, not Leif's scout. Timber home and a relief ship are the win.
VOYAGE TUNING (FEEDS THE GAME BUILD THROUGH data/knobs.json)
Knob | Value | Used by
Departure day of year | 145 | Season clock: 25 May. Leave after the ice.
Last safe day at sea (day of year) | 273 | Season clock: 30 Sep. Still at sea in October is a loss.
Daily drift with no fix (nm) | 24 | Drift: added to the leg each day; partial halves, clean refunds
Pace multiplier: crack on | 1.25 | Pace
Pace multiplier: easy | 1 | Pace
Pace multiplier: heave to | 0.15 | Pace: the storm choice
Sail strain per watch cracking on in wind | 0.08 | Ship condition
Sprung strake chance per storm watch running | 0.12 | Ship condition
Sprung strake chance per storm watch hove to | 0.02 | Ship condition
Cask breach chance per rough day | 0.1 | Drink
Sickness chance per person-day, full ration | 0.0005 | Sickness
Sickness chance per person-day, half ration | 0.0015 | Sickness
Sickness chance per person-day, bare bones | 0.004 | Sickness
Death chance per sick person-day when starving | 0.05 | Sickness
Days a sick person stays sick | 5 | Sickness
Fodderless days before an animal dies | 3 | Livestock
Hand-line catch per fishing day (person-days) | 18 | Fishing: three quarters of a day's full ration. Placeholder until the hand-line mini-game (F05)
Morale change per day: full / half / bare rations | 1 / -2 / -5 | Morale (read as three numbers)
Morale change: storm day | -3 | Morale
Morale change: a death | -10 | Morale
Morale change: landfall | 8 | Morale
Morale change: clean fix | 2 | Morale
Starvation sickness multiplier | 15 | Sickness: chance multiplier on days with no food
Thirst sickness multiplier | 25 | Sickness: chance multiplier on days with no drink
Hooks carried | 6 | Hand line: a snapped or cut line costs a hook
CAMP TUNING (FEEDS THE GAME BUILD THROUGH data/knobs.json)
Knob | Value | Used by
Work to raise a booth (builder-days) | 16 | Build: a turf-and-timber booth
People sheltered per booth | 8 | Shelter: the unsheltered sicken faster
Your seated joint counts as (builder-days) | 3 | Build: the joint mini-game is the skilled work that holds the frame
Shore fishing per worker-day (person-days) | 6 | Fish: crew working without you
Forage per worker-day (person-days) | 4 | Forage: placeholder until the forage mini-game (F13)
Timber felled per worker-day (units) | 0.05 | Felled, trimmed and hauled to the slip; 4 units open the return
Hay cut per worker-day (units) | 0.15 | Hay, 1 August to mid-October
First hay day (day of year) | 213 | Hay: 1 August
Milk per fed cow per day (person-days) | 2 | Livestock: summer grazing feeds them
Unsheltered sickness multiplier | 3 | Shelter
Tending shortens sickness by (days per tender-day) | 1 | Tend the sick
Camp build ends (day of year, second year) | 145 | This build ends at the second spring; the return voyage comes in Alpha
Booth plots at the camp | 3 | Build queue: booths first, then the longhouse
Work to raise the longhouse (builder-days) | 540 | Build queue: the hall that gets the camp through winter (F17)
First snow (day of year) | 305 | Winter: 1 November. Forage closes, fishing and building slow
Spring thaw (day of year) | 110 | Winter ends: 20 April
Forage and hay season ends (day of year) | 290 | Mid-October
Drying per worker-day (person-days) | 15 | Smoke rack: surplus fresh fish becomes stores (F15)
Dried fish yield | 0.9 | Share of person-days kept when fish is dried
Winter shore fishing factor | 0.3 | Ice and short days
Winter building factor | 0.5 | Frozen ground, short days
Winter milk factor | 0.3 | Cows dry off in winter
Winter sickness factor | 1.5 | Cold
Booth shelter in winter (share) | 0.5 | Booths are summer shelter; the longhouse holds everyone
Unsheltered winter sickness multiplier | 6 | Winter exposure
Death chance per exposed sick person-day in winter | 0.02 | Cold kills the sick without a roof
Hay per head of cattle per winter day (units) | 0.06 | A sheep eats the sheep fodder share of this
Hay needed without a byre (multiplier) | 1.5 | Cattle out in the cold eat more
Work to raise the byre (builder-days) | 160 | Build queue after the longhouse (F17)
Hunt kill chance per hunter-day | 0.07 | Hunt: about the yield of a fisher, but swingier, and it brings hides
Meat per kill (person-days) | 75 | Hunt: one caribou; spoils like fish unless dried
Far grounds kill bonus | 1.4 | Hunt: more caribou away from the camp
Far grounds fear chance per hunter-day | 0.05 | Goodwill / fear: ranging far is seen (F19)
Winter hunting factor | 0.7 | Hunt: deep snow
Stripped patch damage carried to the season (share) | 0.5 | Forage: greedy picking thins every patch until spring
MARKET TUNING (GOODWILL, FEAR, TRADE)
Knob | Value | Used by
First market (days after landing) | 15 | Visitors come once the camp is settled
Market chance per day | 0.06 | Summer and autumn only
Market chance per point of goodwill | 0.01 | Goodwill brings them back sooner
Goodwill cap | 10 | Goodwill clock
Pelts the visitors bring | 3 to 8 | Range per market
Trade value for one pelt | 2 | Before goodwill
Price discount per point of goodwill | 0.05 | Fair dealing makes trade easier
Red cloth strips per trade unit | 20 | One bolt of madder-red cloth
Iron blades per trade unit | 5 | One trade unit of iron
Milk per trade value (person-days) | 10 | Milk is the peace (Pillar P6)
Weapon request chance per market | 0.25 | Once goodwill reaches 2
Weapon sale pelt multiplier | 3 | The temptation
Fear from a weapon sale | 2 | A weapon sale caps fear (Pillar P6)
Bull breaks loose chance (unpenned, no byre) | 0.25 | The saga bull (F21)
Fear from the bull | 2 | Visitors scatter
Fear eased per quiet week | 0.5 | Fear fades slowly when nothing happens
Raid chance per week at the fear cap | 0.3 | Trade breaks; the herd and the crew are at risk
Pelts per cargo unit | 10 | Return cargo
Formulas:
Notes = B8+[Weeks]*7-1
Note on B7: Source: plan authored 9 Oct 2026 from the Vinland systems and mini-game design.

## Pillars
VINLAND
Pillars, fantasy, clocks, and the win
ID | Pillar | Player promise | Fails if | Design owner
P1 | The hold is the game | Every fun verb spends cargo, a watch, or a body. | A mini-game pays out points that do not fit in the hull. | Design
P2 | Latitude, not a chart | Clear nights buy a shorter leg. Fog is missing information, not a blank screen. | The player can win by confirming a menu. | Design
P3 | One controller grammar | Left stick gross, right stick fine, triggers force, B is the safe drop. | A verb invents its own buttons. | Design
P4 | Season is a clock | Leave after the ice. October at sea is a loss. Winter is survival, not travel. | The player can sail whenever. | Design
P5 | The colony is the point | Karlsefni, not Leif. Livestock, a birth, a byre, a market. | The game ends at landfall. | Design
P6 | Trade until it doesn't | Milk and red cloth buy peace. A weapon sale or a killing caps fear. | Natives are a faction toggle. | Design
P7 | The return is the win | Timber home funds the next hull. Two cargoes and one relief ship is the full win. | Score is distance sailed. | Design
P8 | Qualified saga ending | Load everyone and leave rich is allowed, and scored below a living camp. | The game scolds the historical ending. | Design
THREE CLOCKS
Clock | Ticks when | Player lever | Loss | Notes
Season | Each watch and each camp day | Pace: crack on, easy, heave to | Still at sea in October | Late May departure, September last open water
Ship | Weather checks, sail strain, sprung strake | Heave to versus run | Hull lost with no camp behind it | A knarr does not fight a storm
Colony | Rations, hay, fear, relief | Byre, rack, market, who sails home | Winter starve, or fear capped and both hulls gone | A camp that only feeds itself dies when the ship does not return
OUTFITS
Outfit | Silver | Strength | Weakness | Starting feel
Farm household | Low | Livestock, cheese, fodder skill | Small cargo, few fighters | The byre is easier, the hold is tighter
Merchant | High | Red cloth, iron, a second hull if paid | Animals eat the margin | Karlsefni. Trade-rich, forage-poor
Hunter-boat | Medium | Fishing, sealing, Markland pilotage | Weak build, weak diplomacy | Better ring, worse joint
Shipwright's kin | Medium | Hull repair, spare sail, timber grade | Poor foragers | The slipway is the fantasy

## Systems
VINLAND
Systems contract · the economy the mini-games pay into
System | Rule | Input knob | Knob cell | Output | Phase | Backlog
Cargo hold | 24 units. People 0.4, cow 1.5, sheep 0.4. Timber only fits if food was eaten. | Knarr cargo units | 24 | What can sail | Vertical slice | F01
Rations | Full, half, bare bones. Animals have their own ration. Starve the bull, lose the trade good. | Party size | 24 | Morale, sickness, milk | Vertical slice | F01, F46
Drink | Water spoils if a cask is breached. Sour whey keeps. | Drink coverage | 120 | Sea endurance | Vertical slice | F37
Legs | Eriksfjord, Labrador Sea, Helluland, Markland, Furðustrandir, Strait. Hóp is a second summer push. | Open-water nm | 400 | Landfall quality | Production | F11, F27
Watches | Four hours. A good day is six watches if the fix held. | Day's sail nm | 120 | Leg length | Vertical slice | F02
Pace | Crack on, easy, heave to. Heave to is the storm choice. | — | Design | Sail strain, distance | Vertical slice | F38
Drift | No fix, ship walks downwind. Partial fix halves drift. Clean fix refunds it. | — | Mini-game | Extra days, wrong landfall | Vertical slice | F03, F38
Weather deck | Fog, low cloud, following gale, beam sea, storm, drift ice, calm. Shuffled per leg. | — | Content | Which verb is offered | Production | F09
Fishing | Once a day, coastal only. Fresh spoils in three days at sea unless dried on two fair days. | Food coverage | 168 | Food units | Vertical slice | F05, F14, F15
Hay | Cut in late summer or the byre is a tomb. Mild winter is a climate die, not the default. | Winters | 2 | Livestock survival | Production | F16, F47
Goodwill / fear | Trade raises goodwill. Weapon sale, killing, palisade, loose bull raise fear. | Fear cap | 5 | Market or battle | Production | F19, F20, F21
Return gate | Boat shed, seaworthy hull, at least four timber units or equivalent. | Timber to open return | 4 | Route unlock | Alpha | F24, F25
Recruitment | A living crew with a true story recruits better than silver. | Summers | 3 | Second hull | Alpha | F26
Score | Cargo delivered, people alive in both places, goodwill left on the table. | — | Design | Qualified vs full win | Beta | F31, F56
Season clock | Late-May departure, September last open water. Each watch and each camp day ticks. Still at sea in October is a loss. | Full game length | 3 | Departure window, winter onset | Vertical slice | F35
Ship condition | Crack on strains the sail. Storm cards can spring a strake. A repair costs a camp day; a knarr that runs a storm pays twice. | — | Design | Storm risk, repair days | Production | F45
Sickness and morale | Bare-bones rations, wet watches, and deaths move morale. Sick crew cannot stand a watch or take a verb. | Party size | 24 | Who can work | Production | F46
Livestock | Cattle take 1.5 units, sheep 0.4. Fodder at sea, hay in camp. Milk is the trade good that keeps the peace. | Cattle at departure | 2 | Milk, hides, the bull event | Production | F16
Winter camp | Hay, dried food, and shelter checked each winter week. A byre keeps the herd; a longhouse keeps the people. | Winters | 2 | Survival, spring strength | Production | F47
Hold check | Departure load must fit the hull; the return must fit the timber gate. The HoldCheck sheet proves both from the knobs. | Knarr cargo units | 24 | Ship-ready or not | Vertical slice | F01, F53

## HoldCheck
VINLAND
Hold check · does the default load fit the knarr, and does the timber fit going home
CROSSING LENGTH
Item | Value | Note
Route distance (nm) | 1200 | Assumptions hold knobs
Good day's sail (nm) | 120 | Six watches with a held fix
Clean sailing days | 10 | Every fix clean, no weather
Weather and lost-day factor | 1.3 | Fog, drift, heave-to
Planned crossing days | 13 | What the hold must feed
DEPARTURE LOAD · ERIKSFJORD
Line | Count | Units each | Cargo units | Rule
People | 24 | 0.4 | 9.6 | Party size on Assumptions
Cattle | 2 | 1.5 | 3 | Bull included
Sheep and goats | 6 | 0.4 | 2.4
Food units | 2 | 1 | 2 | People × crossing days ÷ person-days per food unit
Drink units | 3 | 1 | 3 | People × crossing days ÷ person-days per drink unit
Fodder units | 2 | 1 | 2 | Cattle-equivalents × crossing days ÷ cattle-days per fodder unit
Trade goods | 2 | 1 | 2 | Red cloth and iron
Total departure load |  |  | 24
Hull capacity |  |  | 24
Spare at departure |  |  | 0 | Full: the intended feel
RETURN · TIMBER HOME
Line | Count | Units each | Cargo units | Rule
Return crew | 10 | 0.4 | 4 | The rest winter the camp
Return food units | 1 | 1 | 1 | Same crossing length as outbound
Return drink units | 2 | 1 | 2
Load before timber |  |  | 7
Room for timber |  |  | 17
Most timber units that fit |  |  | 17
Timber units to open the return |  |  | 4
Return gate |  |  | Opens | Room for 17 timber units against a gate of 4
One food, drink, fodder, or trade unit is one cargo unit by definition. Outbound food is eaten by landfall, which is why timber only fits going home. Tune the knobs on Assumptions; this sheet holds no inputs.

## MiniGames
VINLAND
Mini-game production plan · gamepad-first, one grammar
ID | Verb | Game | Controls | Difficulty is | Success pays | Failure costs | Build order | Backlog | Haptic tell | No-haptic fallback
MG1 | Navigate | Star ring | LS holds ring, RS seats Pole Star, RT raise, LT lower, B abort to partial | Cloud gaps and a false horizon glow | Drift refunded | Ship walks downwind | 1 | F03 | Pulse sharpens as the Pole Star seats; goes slack through cloud | Ring rim brightens and a soft tick sounds when seated
MG2 | Navigate | Sun board | LS turns disk, RS sets peg, RT holds through the roll | Overcast skips it; snatching the shadow keeps yesterday's error | Latitude error shrinks | Error carries | 2 | F04 | Low hum when the shadow tip crosses the gnomon curve | Shadow tip glints; result line names the error in degrees
MG3 | Fish | Hand line | LS pays line, RT sets on the ease, B cuts the line | Current, fog hiding the bite | Meals, hook kept | Hook stock or the fish | 1 | F05 | Bite is a two-beat tug on the left motor; the ease is a release | Line twitches, float dips, bite sound on its own channel
MG4 | Fish | Net | RS throws the arc, both triggers close | School depth in rain; fog until it is under the boat | A day's meals, dryable | Empty throw, day spent | 3 | F14 | Weight builds in both triggers as the school comes under | Water darkens and the surface boils over the school
MG5 | Hunt | Stalk and loose | LS move, RT speed, LB crouch, RB bow, RS lead, A loose, B lower | Noise, wind in the grass, slick draw in rain | Meat and a hide | Wound, or a fear tick if ranging far | 2 | F12 | Heartbeat when the animal is alert; draw resistance on RT | Ear-flick icon on the animal; bowstring creak at full draw
MG6 | Forage | Patch reading | LS walk, RT take, RS sorts the basket | Greedy hold strips the season; bird-island noise meter | Food or a cargo marker | Empty patch, or a vine eaten as calories | 3 | F13 | Soft tick per take, harsh buzz when the take turns greedy | Patch thins in color; basket weight bar on screen edge
MG7 | Build | Joint | LS brace, RS sets peg, RT drives with the grain | Rain shortens the safe drive; grain reported on the trigger | Joint seats, day counts | Split log, day lost | 2 | F07 | Grain resistance rises through RT when driving across it | Grain line on the log turns red when the drive is cross-grain
MG8 | Build | Lift | Both triggers haul, LS braces, B sets down safe | Sway window; surf on the slipway | Wall or mast up | Sick list, cracked timber | 3 | F18 | Sway rhythm alternates between triggers | Rope tension meter at screen edge with a safe band
MG9 | Build | Smoke rack fire | RS keeps the column under the wind | Wind shove, too-hot case hardening | Fish becomes a food unit | Spoiled rack | 4 | F15 | Warmth ramps up; a stutter when the fire case-hardens | Smoke shifts from white to black as heat runs high
MG10 | Sea | Storm bail | No sky game. Hull check, then bail rhythm on RT | Wave sets; skipped ring | Hull holds, blind drift next | Sprung strake, lost cask, man overboard | 2 | F10 | Wave sets arrive as a rolling rumble one beat early | Bucket metronome and a water line on the hull
GAMEPAD GRAMMAR · DO NOT BREAK
Left stick | Gross motion: steer, sweep, draw, place, walk
Right stick | Fine correction: trim, lead, seat a joint, sort a basket
RT | Force or commitment. Haptic is the information channel.
LT | Brake, brace, or a lesser safe result
RB / LB | Swap tool. No wheel.
A | Bite, loose, plant. A commitment.
B | Emergency drop. Saves the person, spends the attempt.
Every haptic tell needs a visual or audio twin before G4 (Backlog F32, Risk R3).

## Backlog
VINLAND
Feature backlog · must-ship is the vertical promise plus the return
ID | Feature | System | Phase | Priority | Owner | Estimate (days) | Depends on | Status | Acceptance
F41 | Paper prototype: star ring and hold | Navigate | Preproduction | Must | Design | 5 | — | Done | Someone who did not design it finds a fix and argues about the hold. [Digital ring prototype stood in for the paper test.]
F42 | Engine bake-off: ring prototype in both engines | Tech | Preproduction | Must | Engineering | 8 | F41 | Done | Engine chosen by week 2 on ring feel and haptic API, not feature lists. [Godot 4.3 chosen 17 Oct 2026 without a bake-off: free, exports PC and web, builds headless for automated tests.]
F43 | Source control, build pipeline, tagged builds | Tech | Preproduction | Must | Engineering | 3 | F42 | Done | Every playtest build is reproducible from a tag. [Repo, tagged-quality builds, headless tests, Windows and Web exports.]
F44 | Art style target: one sea, one camp, one UI frame | Art | Preproduction | Must | Art | 5 | — | Not started | Three paintovers approved: wood, wool, and a ring, not chrome.
F01 | Hold and ration model | Economy | Vertical slice | Must | Engineering | 8 | — | In progress | Cargo units, rations, and spoilage read from Assumptions knobs; no literals in code. [Hold, rations, spoilage and animal fodder run from knobs; HoldCheck arithmetic reproduced and tested.]
F02 | Watch and leg runner | Voyage | Vertical slice | Must | Engineering | 10 | F01 | In progress | Four-hour watches advance a leg; pace and weather resolve per watch. [Six watches a day, six legs, landfalls, playable voyage screen from Eriksfjord to the Strait.]
F03 | Star ring mini-game | Navigate | Vertical slice | Must | Design | 12 | F02 | Done | Fix result (clean, partial, none) feeds drift; playable with haptics off. [Star ring passed the slice playtest after the difficulty retune.]
F04 | Sun board mini-game | Navigate | Vertical slice | Must | Design | 6 | F03 | Not started | Overcast skips it; a snatched shadow keeps yesterday's error.
F05 | Hand-line fishing | Fish | Vertical slice | Must | Design | 8 | F02 | Done | A bite reads through the trigger; a cut line keeps the hook. [Hand line passed the slice playtest after the difficulty retune.]
F06 | One camp day loop | Colony | Vertical slice | Must | Design | 8 | F01 | Done | Morning job queue, one verb, evening tally that changes the hold. [Camp day loop shipped in the slice and extended to a full year.]
F07 | Joint construction | Build | Vertical slice | Must | Engineering | 8 | F06 | Done | Grain reported on RT; a split log costs the day. [Joint passed the slice playtest after the difficulty retune.]
F08 | Gamepad grammar and haptics pass | Controls | Vertical slice | Must | Engineering | 6 | F03 | In progress | Every verb follows the grammar table on MiniGames; no verb invents a button. [Gamepad grammar mapped as input actions with keyboard fallback.]
F35 | Season clock and calendar | Clocks | Vertical slice | Must | Engineering | 4 | F02 | In progress | Watches and camp days tick the calendar; October at sea triggers the loss. [Season clock from 25 May; at sea past 30 Sep is a loss; HUD dial.]
F36 | Hold tally UI | UI | Vertical slice | Must | Art | 5 | F01 | Not started | Hold reads at a glance; every change animates the unit that moved.
F37 | Drink casks, breach, and whey | Economy | Vertical slice | Must | Engineering | 3 | F01 | In progress | A breached cask spoils water; sour whey keeps. [Breach on rough days loses a cask; thirst sickness. Whey not yet modelled.]
F38 | Pace and drift resolution | Voyage | Vertical slice | Must | Engineering | 4 | F03 | In progress | No fix walks downwind; partial halves drift; clean refunds it. [Pace (crack on, easy, heave to) and drift: none walks, partial halves, clean refunds; open water doubles drift.]
F39 | Playtest run log | Tools | Vertical slice | Must | Engineering | 3 | F02 | In progress | Every run writes hold, rations, fixes, and deaths per day to a file. [Daily voyage CSV and per-night ring CSV written to the user folder; 1,200-voyage balance sweep in tests.]
F40 | Haptic pattern library | Controls | Vertical slice | Must | Engineering | 3 | F08 | Not started | Haptic patterns live in data files, tunable without a rebuild.
F61 | Early store page from slice capture | Release | Vertical slice | Should | Production | 3 | F44 | Not started | Page live at G1 so wishlists build for a year.
F09 | Weather deck | Voyage | Production | Must | Design | 8 | F02 | In progress | Seven cards shuffled per leg; each card offers a verb or takes one away. [Seven cards plus fair wind, weighted per leg; card shown at each dawn.]
F10 | Storm bail | Voyage | Production | Must | Design | 5 | F09 | In progress | No sky game in a storm: hull check, then bail rhythm. [Playable: find the leak, bail on the beat, wave sets with early rumble. Novice keyboard holds 100/92/42% (Forgiving/Standard/Hard).]
F11 | Helluland, Markland, Strait legs | Voyage | Production | Must | Design | 10 | F09 | Not started | Each leg has a landfall quality and a named failure.
F12 | Stalk and loose | Hunt | Production | Must | Design | 10 | F06 | In progress | One shot; ranging far can tick fear. [Playable: stalk, freeze when it watches, crouch, scent, draw, aim with sway, loose; near/far grounds with a fear tick. Novice kills 75-79% Forgiving, 50-63% Standard.]
F13 | Forage patch | Forage | Production | Must | Design | 6 | F06 | In progress | A greedy take strips next season's patch. [Playable: pick ripe clumps, greedy picking strips the patch for the season; magnetic hand on easier settings. Novice 100% Forgiving/Standard. Bird-island noise still to come.]
F14 | Net throw | Fish | Production | Should | Design | 5 | F05 | Not started | An empty throw spends the day.
F15 | Drying and smoke rack | Economy | Production | Must | Engineering | 5 | F05 | In progress | Two fair days turn fresh fish into a food unit. [Smoke-and-dry job turns surplus fresh fish into stores on fair days (90% kept). Rack mini-game (MG9) still to come.]
F16 | Livestock, milk, hay | Colony | Production | Must | Engineering | 8 | F01 | In progress | Hay cut in late summer or the byre is a tomb. [Milk from fed cows; hay cut August to mid-October; herd eats hay all winter; no hay kills animals.]
F17 | Byre, longhouse, booths | Build | Production | Must | Art | 8 | F07 | In progress | Three buildings raised with the joint and lift verbs; no tech tree. [Build queue: three booths, the longhouse (540 builder-days), the byre (160). Placeholder drawings.]
F18 | Lift and slipway | Build | Production | Must | Engineering | 6 | F07 | Not started | Slipway can spill a log; a bad lift puts a builder on the sick list.
F19 | Goodwill and fear clocks | Trade | Production | Must | Design | 6 | F16 | In progress | Trade raises goodwill; weapon sale, killing, palisade, loose bull raise fear toward the cap. [Fear clock started: far hunting raises fear (cap 5). Goodwill and the market still to come.]
F20 | Market day | Trade | Production | Must | Design | 6 | F19 | Not started | Milk and red cloth trade; visitors have wants of their own and leave when fear rises.
F21 | Bull and weapon-sale events | Trade | Production | Must | Design | 3 | F20 | Not started | Either event can break the market; neither is a cutscene.
F22 | Four outfits | Meta | Production | Should | Design | 6 | F01 | Not started | Each outfit changes the starting hold and one verb's ease.
F23 | Named crew roles | Colony | Production | Should | Design | 5 | F22 | Not started | Roles decide who can stand a watch, take a verb, or sail home.
F45 | Ship strain and hull damage | Clocks | Production | Must | Engineering | 5 | F09 | In progress | Crack on strains the sail; storms can spring a strake; repair costs a day. [Sail strain and sprung strakes; repair one level at each landfall.]
F46 | Sickness and morale | Colony | Production | Must | Design | 4 | F01 | Not started | Bare-bones rations and wet watches make sick crew who cannot work.
F47 | Winter camp loop and starvation check | Colony | Production | Must | Engineering | 6 | F16 | In progress | Each winter week checks hay, food, and shelter; starvation ends the run. [Seasons and years; first snow 1 Nov, thaw 20 Apr; winter shelter, work, sickness and cold deaths. Year sweeps: a planning camp loses no one, a summer-only camp about 8.]
F48 | Birth event | Colony | Production | Should | Design | 2 | F23 | Not started | A first-winter birth is possible, never guaranteed.
F49 | Audio implementation pass | Audio | Production | Must | Audio | 10 | F02 | Not started | Wind, sea, hull creak, mallet, market bed. Haptic first, speaker second.
F50 | Save system | Tech | Production | Must | Engineering | 5 | F02 | In progress | Watch-level autosave at sea, day-level in camp, three rolling slots. [Autosave every watch at sea and every day ashore, three rolling slots written via temp file, exact-replay loads, Continue on the title.]
F51 | Main menu, options, pause | UI | Production | Must | Engineering | 4 | F36 | Not started | Options cover remaps, haptic strength, text size, and ironman.
F52 | First-fjord onboarding | Controls | Production | Must | Design | 5 | F08 | Not started | The first leg teaches the grammar without a tutorial screen.
F53 | Eriksfjord loadout | Meta | Production | Must | Design | 4 | F01 | Not started | Player picks people, animals, and goods against the hull before leaving.
F59 | Cultural and historical review | Content | Production | Must | Production | 3 | F20 | Not started | Consultant reviews the market, trade lines, and visitors before G2.
F63 | Localization-ready string table | Words | Production | Should | Engineering | 2 | F51 | Not started | All text in one table; Icelandic names flagged do-not-translate.
F65 | External playtest rounds | Playtest | Production | Must | Production | 4 | F39 | Not started | Two rounds with run logs and notes; honoraria on Assumptions.
F24 | Return voyage and autumn bias | Route | Alpha | Must | Engineering | 8 | F11 | Not started | Autumn bias: longer nights and worse weather on the way home.
F25 | Timber appraisal and cargo sale | Route | Alpha | Must | Design | 5 | F18 | Not started | Timber grade and amount set what the cargo buys at home.
F26 | Recruitment and second hull | Route | Alpha | Must | Design | 6 | F25 | Not started | A living crew and a true story recruit better than silver.
F27 | Hóp push | Voyage | Alpha | Should | Design | 6 | F11 | Not started | Second-summer site. First cut if Production slips.
F28 | Thorhall split | Colony | Alpha | Could | Design | 4 | F21 | Not started | A party leaves to look for grapes. Could cut.
F29 | Sealing specialty | Fish | Alpha | Could | Design | 4 | F05 | Not started | Hunter-boat outfit specialty. Could cut.
F30 | Full three-summer sim | Meta | Alpha | Must | Engineering | 8 | F24 | Not started | A run goes outfit to score with no debug commands.
F54 | Mouse and keyboard fallback | Controls | Alpha | Should | Engineering | 4 | F08 | Not started | Every verb completable without a gamepad; not tuned for it.
F55 | Economy tuning pass from run logs | Economy | Alpha | Must | Design | 5 | F39 | Not started | Knob changes made on Assumptions, backed by logged runs.
F64 | Regression pass list per gate | QA | Alpha | Must | QA | 4 | F30 | Not started | Each gate has a written pass list run on the tagged build.
F31 | Score and saga ending | Meta | Beta | Must | Design | 3 | F30 | Not started | Qualified ending scored below a living camp, never scolded.
F32 | Accessibility: remaps, hold-to-repeat, no-haptic fallback | Controls | Beta | Must | Engineering | 5 | F08 | Not started | Remaps, hold-to-repeat, and a no-haptic twin for every tell.
F33 | Difficulty pass on sky and stalk | Polish | Beta | Must | Design | 6 | F30 | In progress | Forgiveness tuned from playtest 2 logs. [Difficulty levels and novice-player tests in place from the first playtest; tune again from real play logs.]
F56 | Ending cards and saga text | Words | Beta | Must | Design | 3 | F31 | Not started | One card per ending type, in saga voice.
F57 | Performance pass and min-spec | Tech | Beta | Must | Engineering | 4 | F30 | Not started | Holds the frame-rate target on Steam Deck class hardware.
F58 | Steam integration | Release | Beta | Should | Engineering | 4 | F50 | Not started | Achievements, cloud saves, controller configuration.
F34 | Store page, trailer, day-one notes | Release | Polish and ship | Must | Production | 5 | F31 | Not started | Trailer is a fix in fog, a joint, and timber leaving the slip.
F60 | Credits and legal notices | Release | Polish and ship | Must | Production | 1 | F34 | Not started | Engine, font, and audio licenses; consultant credit.
F62 | Crash reporting and day-one patch buffer | Release | Polish and ship | Must | Engineering | 3 | F57 | Not started | Crash logs reach the studio; one patch staged before launch.
|  |  | Total estimate (days) |  |  | 351
|  |  | Must-ship days |  |  | 306
|  |  | Should / could days |  |  | 45
|  |  | Done days |  |  | 52
|  |  | Must-ship done |  |  | 16.99%
CAPACITY CHECK · FEATURE DAYS AGAINST BUDGETED PERSON-WEEKS
Owner |  | Backlog days | Capacity (days) | Load | Read
Design |  | 166 | 200 | 83% | Over
Engineering |  | 137 | 220 | 62.27% | Tight
Art |  | 18 | 155 | 11.61% | OK
Audio |  | 10 | 60 | 16.67% | OK
QA |  | 4 | 90 | 4.444% | OK
Production |  | 16 | 160 | 10% | OK
All owners |  | 351 | 885 | 39.66% | OK
Phase |  | Backlog days | Person-days | Load | Read
Preproduction |  | 21 | 80 | 26.25% | OK
Vertical slice |  | 91 | 170 | 53.53% | OK
Production |  | 151 | 320 | 47.19% | OK
Alpha |  | 54 | 130 | 41.54% | OK
Beta |  | 25 | 115 | 21.74% | OK
Polish and ship |  | 9 | 70 | 12.86% | OK
Estimates are feature-build days only. Iteration, bug fixing, content, and meetings live in the remaining capacity, so a load above 60% is tight and above 80% will slip. Fix by cutting Could items, moving a row to a later phase, or adding weeks on Assumptions.

## Schedule
VINLAND
Phase schedule · dates flow from Assumptions
Phase | Weeks | Start | End | Exit gate | Demo | Risk if slipped | Gate
Preproduction | 8 | 2026-11-02 | 2026-12-27 | Pillar doc signed. Paper ring playable on a table. Slice scope frozen. | Internal table read | Scope still soft. Do not hire the full art week yet. | G0
Vertical slice | 10 | 2026-12-28 | 2027-03-07 | One sea leg, a fix, a fish, a joint, a hold that changed because of them. | Playable slice, friends | If the ring is not fun, stop. Nothing downstream saves a bad fix. | G1
Production | 18 | 2027-03-08 | 2027-07-11 | All six legs, five verbs, market, hay, slipway. No new verbs after this. | External playtest 1 | Hóp and sealing are the relief valves. | G2
Alpha | 6 | 2027-07-12 | 2027-08-22 | Feature complete. One three-summer run from outfit to score. | External playtest 2 | Economy exploits become the work. | G3
Beta | 6 | 2027-08-23 | 2027-10-03 | Difficulty and accessibility locked. Content freeze. | Release candidate | No new events. Tune only. | G4
Polish and ship | 4 | 2027-10-04 | 2027-10-31 | Store page live. Trailer cut. Day-one patch list empty enough to ship. | Ship | A slipped ship date costs the autumn window in the marketing story, not the design. | G5
Ship date | 2027-10-31
Days, plan date to ship | 387
MILESTONE CALENDAR CHECK
The start date and the six week counts live on Assumptions. This sheet only adds. If a phase overruns, add weeks there, do not type a date here.
Holidays are not carved out of phase weeks. This plan crosses Thanksgiving, the December holidays, and summer. Budget one rest week per phase by adding it on Assumptions (Risk R13).
Formulas:
Start = [End, row above]+1
End = [Start]+[Weeks]*7-1

## Timeline
VINLAND
Timeline · week by week from Schedule; add weeks on Assumptions and the bars move
Week | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Week of | time axis 2026-11-02 to 2027-12-20
Month |  |  | 2026-11-02: Nov; 2026-12-07: Dec; 2027-01-04: Jan; 2027-02-01: Feb; 2027-03-01: Mar; 2027-04-05: Apr; 2027-05-03: May; 2027-06-07: Jun; 2027-07-05: Jul; 2027-08-02: Aug; 2027-09-06: Sep; 2027-10-04: Oct; 2027-11-01: Nov; 2027-12-06: Dec
Preproduction | 2026-11-02 | 2026-12-27 | bar: 2026-11-02 to 2026-12-21
Vertical slice | 2026-12-28 | 2027-03-07 | bar: 2026-12-28 to 2027-03-01
Production | 2027-03-08 | 2027-07-11 | bar: 2027-03-08 to 2027-07-05
Alpha | 2027-07-12 | 2027-08-22 | bar: 2027-07-12 to 2027-08-16
Beta | 2027-08-23 | 2027-10-03 | bar: 2027-08-23 to 2027-09-27
Polish and ship | 2027-10-04 | 2027-10-31 | bar: 2027-10-04 to 2027-10-25
Gates | bar: 2026-12-21; 2027-03-01; 2027-07-05; 2027-08-16; 2027-09-27; 2027-10-25
This week
Ship lands in week 52 of 60 shown. ◆ marks the week a gate falls due; ▲ marks the current week.

## TeamBudget
VINLAND
Team loading and cost · weeks are inputs, rates come from Assumptions
Role | Rate / week | Preproduction | Vertical slice | Production | Alpha | Beta | Polish and ship | Person-weeks | Labor
Design | 1800 | 6 | 8 | 14 | 6 | 4 | 2 | 40 | 72000
Engineering | 2200 | 4 | 10 | 18 | 6 | 4 | 2 | 44 | 96800
Art | 1700 | 2 | 6 | 14 | 4 | 3 | 2 | 31 | 52700
Audio | 1600 | 0 | 2 | 4 | 2 | 2 | 2 | 12 | 19200
QA | 1200 | 0 | 2 | 4 | 4 | 6 | 2 | 18 | 21600
Production | 1900 | 4 | 6 | 10 | 4 | 4 | 4 | 32 | 60800
Person-weeks per phase | sum of roles | 16 | 34 | 64 | 26 | 23 | 14 | 177 | 323100
Average team size (FTE) | person-weeks ÷ weeks | 2 | 3.4 | 3.5556 | 4.3333 | 3.8333 | 3.5 | 3.4038
PHASE ROLLUP · DASHBOARD READS THIS BLOCK
Phase | Calendar weeks | Design | Engineering | Art | Audio | QA | Production | Person-weeks | Labor
Preproduction | 8 | 6 | 4 | 2 | 0 | 0 | 4 | 16 | 30600
Vertical slice | 10 | 8 | 10 | 6 | 2 | 2 | 6 | 34 | 63600
Production | 18 | 14 | 18 | 14 | 4 | 4 | 10 | 64 | 118800
Alpha | 6 | 6 | 6 | 4 | 2 | 4 | 4 | 26 | 46400
Beta | 6 | 4 | 4 | 3 | 2 | 6 | 4 | 23 | 39100
Polish and ship | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 14 | 24600
Labor subtotal | [8 empty] | 323100
Overhead | [7 empty] | 15% | 48465
Outsource art | [8 empty] | 18000
Music and foley | [8 empty] | 12000
Store, trailer, legal | [8 empty] | 4000
Playtest honoraria | [8 empty] | 2500
Cultural and historical consultant | [8 empty] | 3000
Platform fee (Steam Direct) | [8 empty] | 100
Subtotal before contingency | [8 empty] | 411165
Contingency | [7 empty] | 12% | 49339.8
FULLY LOADED | [8 empty] | 460504.8
Dashboard and Breakeven link
B35 is the labor subtotal, B36 is fully loaded, B37 is cash outlay excluding labor (with contingency). Dashboard and Breakeven read these three cells.
Labor subtotal | 323100
Fully loaded | 460504.8
Cash outlay excl. labor | 98632.8

## Breakeven
VINLAND
Break-even · what the plan costs in copies sold
NET PER UNIT
Item | Value | Note
List price | 19.99 | Assumptions
Realized price | 15.992 | After launch discounts, regional pricing, sales-tax netting
After refunds | 14.7126
Blended store share | 29% | Steam and itch.io weighted by the sales mix
Net to studio per unit | 10.446 | Before income tax
BREAK-EVEN
Item | Value | Note
Fully loaded cost | 460504.8 | Labor at market rates plus every cost line
Units to break even, fully loaded | 44085 | Pays everyone at the rates on Assumptions
Cash outlay excluding labor | 98632.8 | Overhead, outsourcing, fees, contingency
Units to recover cash | 9443 | The floor for a self-funded solo developer
Gross sales at full break-even | 881259.15 | List price × units, before every deduction
SALES SCENARIOS
Units sold | Net revenue | Vs fully loaded | Vs cash outlay | Read
2000 | 20891.9488 | -439612.8512 | -77740.8512 | Short of cash
5000 | 52229.872 | -408274.928 | -46402.928 | Short of cash
10000 | 104459.744 | -356045.056 | 5826.944 | Cash back; labor partly unpaid
25000 | 261149.36 | -199355.44 | 162516.56 | Cash back; labor partly unpaid
50000 | 522298.72 | 61793.92 | 423665.92 | Pays everyone; funds the next hull
Labor rates price the work at market value. A solo developer drawing no salary needs only the cash line to stay whole; the fully loaded line is what the work is worth. Revenue inputs are planning assumptions on Assumptions, not a forecast. Income tax is not modeled.

## Milestones
VINLAND
Milestone acceptance · a phase is done when the gate is true, not when the week ends
Gate | Phase end | Must be true | Evidence | Owner | Status | Backlog proof | Risks watched
G0 | 2026-12-27 | Pillars signed. Paper prototype of the ring judged fun by someone who did not design it. | Digital ring prototype, 17 Oct 2026 | Design | Passed | F41, F42, F43, F44 | R8, R9
G1 | 2027-03-07 | Slice: leave a fjord, miss a fix, fish, dry nothing, build one joint, see the hold change. | Slice build v2, playtest 17 Oct 2026 ("much better") | Engineering | Passed | F01, F02, F03, F04, F05, F06, F07, F08, F35, F36, F37, F38, F39, F40, F61 | R1, R2, R12, R16
G2 | 2027-07-11 | All verbs in, market can break, hay can kill the herd, slipway can spill a log. | Playtest 1 report | Design | In progress | F09, F10, F11, F12, F13, F14, F15, F16, F17, F18, F19, F20, F21, F22, F23, F45, F46, F47, F48, F49, F50, F51, F52, F53, F59, F63, F65 | R4, R5, R6, R11, R13, R15
G3 | 2027-08-22 | Three-summer run completable. Qualified ending and full ending both reachable. | Alpha save set | Production | Not started | F24, F25, F26, F27, F28, F29, F30, F54, F55, F64 | R7, R10
G4 | 2027-10-03 | Remap works. No-haptic fallback taught. No must-ship bug open. | Beta bug list | QA | Not started | F31, F32, F33, F56, F57, F58 | R3, R14
G5 | 2027-10-31 | Ship build, trailer, store copy, day-one notes. | Release folder | Production | Not started | F34, F60, F62 | —
A gate is Passed only when every Must row in its Backlog proof is Done or formally Cut, and the evidence exists in the release folder.

## Risks
VINLAND
Risks · score is likelihood times impact, both 1 to 5
ID | Risk | Likelihood | Impact | Score | Mitigation | Owner | Watch | Early warning | Status
R1 | Star ring is not fun | 3 | 5 | 15 | Stop at the slice. Retune forgiveness before any other verb. [17 Oct 2026: first playtest failed every mini-game. Retuned: Forgiving / Standard / Hard difficulty, guided prompts, keyboard wind-up, novice-player bots now gate every build.] | Design | G1 | Table testers stop seating stars after three tries | Watching
R2 | Hold math is trivial or cruel | 3 | 4 | 12 | Log every slice run. Tune food coverage on Assumptions, not in code literals. | Design | G1 | Slice runs end with the hold always full or never touched | Open
R3 | Haptics-only tells lock out players | 2 | 4 | 8 | No-haptic fallback is must-ship, not a patch. | Engineering | G4 | Testers with haptics off miss bites or split joints | Open
R4 | Scope creep into a second site | 4 | 3 | 12 | Hóp is Should. Cut it before cutting the return. | Production | G2 | Hóp tasks show up in Production plans | Open
R5 | Art style slips into illustration | 2 | 3 | 6 | UI is wood, wool, and a ring. Outsource budget is capped on Assumptions. | Art | G2 | Outsourced pieces come back painterly | Open
R6 | Native trade reads as a shooter | 2 | 5 | 10 | Market is the verb. The bow turns outward only after fear caps. | Design | G2 | Testers reach for the bow before the market | Open
R7 | Solo schedule slips a phase | 3 | 4 | 12 | Add weeks on Assumptions. Do not silently eat polish. | Production | G3 | Two straight weeks behind on backlog burn | Open
R8 | Engine choice burns the slice | 2 | 4 | 8 | Pick at week 2. Ring prototype is the decider, not a feature list. | Engineering | G0 | No engine pick by the end of week 2 | Open
R9 | Historical pedantry stalls play | 2 | 2 | 4 | Saga disagreement is a footnote, not a blocker. Karlsefni spine is locked. | Design | G0 | Design debates cite sagas more than playtests | Open
R10 | Return voyage feels like a commute | 3 | 4 | 12 | Autumn bias: longer nights, worse weather. The reversal is the content. | Design | G3 | Testers autopilot or skip return legs | Open
R11 | Indigenous people read as a prop or a stereotype | 3 | 5 | 15 | Fund the consultant review before G2 (Backlog F59). Market visitors have wants of their own. Keep saga terms in saga-voice text with context, not as faction labels. | Design | G2 | Consultant flags; visitors exist only to trade or fight | Open
R12 | Store page goes up too late to build wishlists | 4 | 4 | 16 | Store page live at the end of the slice (F61). One-leg demo for Steam Next Fest between Alpha and Beta. | Production | G1 | Wishlists flat for a month after the page goes live | Open
R13 | Lead burnout across a 52-week run | 3 | 4 | 12 | One rest week per phase added on Assumptions. No crunch in Polish; cut order applies instead. | Production | G2 | A skipped rest week; estimates slipping on easy rows | Open
R14 | Gamepad-first narrows the audience | 2 | 3 | 6 | Mouse fallback is Should (F54). Store page says controller recommended; Steam Deck Verified target. | Design | G4 | Store page comments ask for mouse support | Open
R15 | Watch-level autosave corrupts a run | 2 | 4 | 8 | Three rolling slots, write-then-rename, load test in every regression pass (F50, F64). | Engineering | G2 | Any failed load in a playtest log | Open
R16 | Cash runs out before ship | 3 | 5 | 15 | Breakeven reviewed at every gate. Phase cost share on Dashboard is the burn check. Cut order applies to spend as well as scope. | Production | G1 | Spend runs ahead of the phase share on Dashboard | Open

## Content
VINLAND
Content pipeline · what has to exist before a phase can exit
Bucket | Slice need | Production need | Ship need | Notes | Owner | Outsource?
Sky | One clear night, one clouded | Fog false glow, twilight short night, storm skip | Autumn return sky | Stars are marks, not a planetarium | Art | Ships and UI frames, sky plates
Sea | One coastal leg, one calm | Ice, beam sea, gale, calm oars | Autumn storm bias | Legs are a chain, not an open map | Design / Art | No
Camp | Booth footprint | Byre, longhouse, rack, palisade, slip | Worn winter camp | Job queue, not a tech tree | Art | No
Creatures | One fish | Salmon, deer, birds, bull | Seal for hunter outfit | No bestiary screen | Art | Creature models if over budget
People | Crew silhouettes | Four outfits, named roles, market visitors | Second-summer recruits | Women are roles, not passengers | Art | Silhouette pass only
UI | Ring, hold tally | Rations, fear, season | Score and saga ending | Wood and wool, not chrome | Art | UI frames (Assumptions B34)
Audio | Wind, one bite, mallet click | Hull creak, market, hay scythe | Return theme, trailer stem | Haptic first, speaker second | Audio | Music and foley (Assumptions B35)
Words | Fix result line | Event lines, trade lines, birth | Ending cards | No scolding the historical ending | Design | No
Haptics | Ring seat, bite, grain | One pattern per mini-game tell | Tuned strengths, no-haptic twins | Haptics are content, authored like sound | Engineering | No
Store and marketing | Slice screenshots, capsule draft | Store page live, demo build | Trailer, final capsules, press kit | Trailer: fix in fog, a joint, timber leaving | Production | Capsule art
Localization | String table exists | All text in the table | English locked; second language if the date holds | Icelandic names do not translate | Production | Translation, post-ship

## Release
VINLAND
Release plan · PC, gamepad-first, a single-player run of three summers
Item | Decision | When | Owner
Platform | PC first. Gamepad required for the intended feel. Mouse is a fallback, not the target. | G0 | Production
Engine | Choose Godot 4 or Unity at week 2, based on which ships the ring prototype faster. | Week 2 | Engineering
Save | Watch-level autosave on the voyage. Day-level in camp. Ironman is a toggle, not the default. | G2 | Engineering
Session | A leg is a sitting. A summer is an evening. The full game is three evenings. | G1 | Design
Price stance | Premium single purchase. No energy, no hull repair packs. | G0 | Production
Age and tone | Trade can become a fight. No gore gallery. The bull and the birth are the tonal range. | G2 | Design
Languages | English at ship. Icelandic names kept. A second language only if the ship date holds. | G4 | Production
Trailer | One fix in fog, one joint, one timber cargo leaving the slip. | G5 | Production
Day one | Remap, no-haptic, and a known-issues note if the autumn bias is still sharp. | G5 | QA
Post-ship | No second site promised. A Markland fishing variant is the only safe follow-up. | After ship | Design
Storefronts | Steam is primary. itch.io carries the same build for players who already follow nickdoneysr there. The sales mix lives on Assumptions. | G1 | Production
Price | Premium at $19.99. Launch discount no deeper than the realized-price factor on Assumptions. | G3 | Production
Wishlists | Store page live at the end of the vertical slice so wishlists build for a full year before ship. | G1 | Production
Demo | One-leg demo built from the slice for Steam Next Fest between Alpha and Beta. Demo saves do not carry over. | G3 | Production
Steam Deck | Target Deck Verified: gamepad-native, legible text at 800p, no launcher. | G4 | Engineering
Content rating | Complete the store's content survey (and IARC where a store requires it) at Beta. Disclose trade violence and animal death. | G4 | Production
Achievements | Tied to saga beats and the full win, never to grinding. | G4 | Design
Accessibility statement | Store page lists remaps, no-haptic mode, hold-to-repeat, and text size. | G5 | Production

## Revisions
VINLAND
Revision log · what changed in this pass and why
Date | Sheet | Change | Why
2026-10-16 | TeamBudget | Fixed the stale "Dashboard labor link" note (it pointed at H20 and H26) and removed a stray =J29 sitting in the Playtest honoraria row. | The note sent readers to the wrong cells; the stray value looked like a cost.
2026-10-16 | TeamBudget | Renamed row 11 to "Person-weeks per phase" and added an average-team-size (FTE) row. | Row 11 was labeled a check against Assumptions but only summed person-weeks.
2026-10-16 | TeamBudget | Added consultant and Steam Direct fee lines; Fully Loaded moved to J31 (named range updated); added cash outlay excluding labor (B37). | Two real costs were missing; cash outlay drives the self-funded break-even.
2026-10-16 | Assumptions | Added hold loading knobs, release and revenue inputs, sales scenarios, project notes, and an expanded how-to-read block. | Every new sheet reads its inputs from here, keeping one input sheet.
2026-10-16 | Systems | Added Season clock, Ship condition, Sickness and morale, Livestock, Winter camp, and Hold check rows, plus a Backlog column. | Three clocks on Pillars had no system rows; every system now traces to backlog IDs.
2026-10-16 | HoldCheck | New sheet: departure load against the hull, return room against the timber gate. | Proves the default party fits the knarr ("a hold that is already full") and that the return can open.
2026-10-16 | MiniGames | Added Backlog link, Haptic tell, and No-haptic fallback for all ten mini-games. | Risk R3 and F32 require a no-haptic twin for every tell; none were specified.
2026-10-16 | Backlog | Grew from 34 to 65 items, added Status and Acceptance columns, phase/owner/status dropdowns, done tracking, and a capacity check by owner and phase. | Preproduction had no rows; save, menus, audio, onboarding, season, hull, winter, review, and release work were missing.
2026-10-16 | Schedule | Added a Gate column, days from plan date to ship, and a holiday note. | Ties dates to gates; the plan crosses three holiday periods with no rest weeks.
2026-10-16 | Timeline | New sheet: a 60-week bar chart driven by Schedule, with gate and current-week markers. | A visual of the phase plan that redraws when weeks change.
2026-10-16 | Breakeven | New sheet: net per unit, break-even units (fully loaded and cash only), five sales scenarios. | The plan had cost but no revenue view.
2026-10-16 | Milestones | Added Status (dropdown), Backlog proof, and Risks watched columns plus a pass rule. | A gate now has a checkable definition of done.
2026-10-16 | Risks | Added R11 to R16, Early warning and Status columns; extended the heat scale and filter. | Representation, discoverability, burnout, input reach, save safety, and cash were unlisted.
2026-10-16 | Content | Added Owner and Outsource columns and Haptics, Store and marketing, Localization rows. | Outsource budget lines on Assumptions had no content mapped to them.
2026-10-16 | Release | Added storefronts, price, wishlists, demo, Steam Deck, content rating, achievements, accessibility statement. | Launch decisions beyond the build were missing.
2026-10-16 | Dashboard | Backlog counts widened to the new range; break-even KPI added; Health Checks block with status colors. | One page now shows scope load, hold math, revenue, risk, and gate status.