## Summary
VINLAND · ART
Summary · how much art, when it is needed, and how much is done (reads the Status column)
BY PHASE · PAINT IN THIS ORDER
Phase | Assets | Must | Hours | Hours done | Hours left | Done | Gate
Preproduction | 6 | 5 | 33 | 0 | 33 | 0% | G0
Vertical slice | 88 | 85 | 367 | 0 | 367 | 0% | G1
Production | 127 | 106 | 737 | 0 | 737 | 0% | G2
Alpha | 16 | 6 | 63 | 0 | 63 | 0% | G3
Beta | 18 | 17 | 119 | 0 | 119 | 0% | G4
Polish and ship | 3 | 1 | 8 | 0 | 8 | 0% | G5
All phases | 258 | 220 | 1327 | 0 | 1327 | 0%
AGAINST THE PLAN
Measure | Value | Source
Art person-weeks in the plan | 31 | TeamBudget: Art row, all phases (from the plan workbook)
Hours per person-week | 40 | Planning assumption; change it to your real week
Planned art hours | 1240 | Person-weeks × hours
Estimated hours on this list | 1327 | Sum of the Est. hours column
Hours flagged for outsourcing | 399 | Rows marked Outsource "Yes"
In-house hours if outsourcing happens | 928 | What is left for you
Fit (in-house hours ÷ planned hours) | 74.84% | Over 100% means cut Could rows, outsource more, or add art weeks
BY CATEGORY
Category | Assets | Must | Hours | Hours done | Hours left | Done | ID prefix
Style targets | 6 | 5 | 33 | 0 | 33 | 0% | STY
Sky plates and celestial | 16 | 13 | 65 | 0 | 65 | 0% | SKY
Clouds and fog layers | 7 | 7 | 23 | 0 | 23 | 0% | CLD
Sea, ice and wildlife | 10 | 7 | 44 | 0 | 44 | 0% | SEA
Coasts by leg | 13 | 11 | 88 | 0 | 88 | 0% | CST
The knarr and other vessels | 13 | 12 | 52 | 0 | 52 | 0% | SHP
Weather and water effects | 7 | 6 | 14 | 0 | 14 | 0% | WFX
Navigation mini-games (star ring, sun board) | 10 | 10 | 36 | 0 | 36 | 0% | NAV
Fishing (hand line, net) | 11 | 9 | 53 | 0 | 53 | 0% | FSH
Hunting (stalk and loose) | 8 | 7 | 53 | 0 | 53 | 0% | HNT
Foraging (patch reading) | 8 | 5 | 40 | 0 | 40 | 0% | FOR
Building (joint, lift, smoke rack) | 14 | 14 | 58 | 0 | 58 | 0% | BLD
Storm bail | 6 | 6 | 27 | 0 | 27 | 0% | BAL
Camp: ground, seasons and buildings | 19 | 17 | 127 | 0 | 127 | 0% | CMP
Livestock | 5 | 3 | 41 | 0 | 41 | 0% | ANI
Crew and named characters | 8 | 5 | 107 | 0 | 107 | 0% | CHR
Market and visitors (consultant review) | 5 | 4 | 75 | 0 | 75 | 0% | MKT
Leg map | 4 | 4 | 24 | 0 | 24 | 0% | MAP
Eriksfjord loadout | 4 | 3 | 40 | 0 | 40 | 0% | LOD
UI kit (wood and wool) | 9 | 9 | 23 | 0 | 23 | 0% | UIK
HUD instruments | 11 | 11 | 27 | 0 | 27 | 0% | HUD
Resource and item icons | 6 | 4 | 26 | 0 | 26 | 0% | ICN
Event and weather card illustrations | 25 | 21 | 103 | 0 | 103 | 0% | EVT
Ending cards and score | 6 | 6 | 59 | 0 | 59 | 0% | END
Title and menus | 8 | 6 | 50 | 0 | 50 | 0% | MNU
Particle textures | 3 | 3 | 6 | 0 | 6 | 0% | VFX
Store and marketing art | 16 | 12 | 33 | 0 | 33 | 0% | MKG
BY STATUS
Status | Assets | Hours
Not started | 258 | 1327
Sketch | 0 | 0
In progress | 0 | 0
Review | 0 | 0
Final | 0 | 0
Imported | 0 | 0
Cut | 0 | 0

## Slice First
VINLAND · ART
Start here · the art the vertical slice needs, in the order the build will use it
ID | Asset | Export size | Priority | Hours | Why now
STY-01 | Sea style target paintover | 1920×1080 | Must | 10 | Locks the look before anything else is finished (gate G0).
STY-02 | Camp style target paintover | 1920×1080 | Must | 10 | Locks the look before anything else is finished (gate G0).
STY-03 | UI style target paintover | 1920×1080 | Must | 6 | Locks the look before anything else is finished (gate G0).
STY-04 | Palette swatch sheet | 1024×512 | Must | 2 | Locks the look before anything else is finished (gate G0).
STY-05 | Character scale and proportion sheet | 1920×1080 | Must | 4 | Locks the look before anything else is finished (gate G0).
STY-06 | Greyscale readability test | 1920×1080 | Should | 1 | Locks the look before anything else is finished (gate G0).
SKY-01 | Sky plate: clear day | 1920×1080 | Must | 5 | The voyage and the star ring need these skies.
SKY-03 | Sky plate: fog | 1920×1080 | Must | 4 | The voyage and the star ring need these skies.
SKY-06 | Sky plate: summer twilight | 1920×1080 | Must | 5 | The voyage and the star ring need these skies.
SKY-07 | Sky plate: clear night | 1920×1080 | Must | 5 | The voyage and the star ring need these skies.
SKY-08 | Sky plate: clouded night | 1920×1080 | Must | 4 | The voyage and the star ring need these skies.
SKY-13 | Sky plate: camp summer and autumn | 1920×1080 | Must | 7 | The voyage and the star ring need these skies.
SKY-14 | Sun disc with glow | 256×256 | Must | 1 | The voyage and the star ring need these skies.
SKY-16 | Voyage night star field | 1920×1080 | Must | 2 | The voyage and the star ring need these skies.
CLD-01 | Cloud band: fair weather | 3840×540 | Must | 4 | Fog and cloud gaps make the ring hard; without them there is no difficulty.
CLD-05 | Fog sheets | 3840×1080 | Must | 4 | Fog and cloud gaps make the ring hard; without them there is no difficulty.
CLD-06 | Cloud gap overlays for the ring | 1920×1080 | Must | 4 | Fog and cloud gaps make the ring hard; without them there is no difficulty.
CLD-07 | False horizon glow | 1920×300 | Must | 1 | Fog and cloud gaps make the ring hard; without them there is no difficulty.
SEA-01 | Sea band far: calm | 3840×300 | Must | 3 | The first sea leg.
SEA-02 | Sea band far: swell | 3840×300 | Must | 3 | The first sea leg.
SEA-05 | Sea band near with foam | 3840×400 | Must | 12 | The first sea leg.
SEA-06 | Bow wake and hull foam | 512×256 per frame | Must | 3 | The first sea leg.
SHP-01 | Knarr hull (side view) | 1400×560 | Must | 12 | The knarr is on screen for the whole voyage.
SHP-02 | Mast and yard | 400×900 | Must | 2 | The knarr is on screen for the whole voyage.
SHP-03 | Sail states | 900×800 | Must | 6 | The knarr is on screen for the whole voyage.
SHP-05 | Steering oar | 160×520 | Must | 1 | The knarr is on screen for the whole voyage.
SHP-08 | Deck cargo stack states | 700×260 | Must | 5 | The knarr is on screen for the whole voyage.
SHP-10 | Crew on deck | 80×140 each | Must | 6 | The knarr is on screen for the whole voyage.
SHP-13 | Ship token for the map | 128×128 | Must | 1 | The knarr is on screen for the whole voyage.
NAV-01 | Star ring instrument | 900×900 | Must | 10 | The ring is the make-or-break test of the slice.
NAV-02 | Ring notch highlight and seat glow | 900×900 | Must | 2 | The ring is the make-or-break test of the slice.
NAV-03 | Hands holding the ring | 600×700 each | Must | 4 | The ring is the make-or-break test of the slice.
NAV-04 | Pole Star and star marks | 64×64 each | Must | 2 | The ring is the make-or-break test of the slice.
NAV-05 | Ring horizon line | 1920×200 | Must | 1 | The ring is the make-or-break test of the slice.
NAV-06 | Fix result marks | 256×256 | Must | 2 | The ring is the make-or-break test of the slice.
NAV-07 | Sun board dial | 900×900 | Must | 8 | The ring is the make-or-break test of the slice.
NAV-08 | Gnomon curve inlays | 900×900 | Must | 2 | The ring is the make-or-break test of the slice.
NAV-09 | Gnomon shadow and tip glint | 64×512 | Must | 1 | The ring is the make-or-break test of the slice.
NAV-10 | Sun board peg and water bowl | 1400×1000 bowl, 64×128 peg | Must | 4 | The ring is the make-or-break test of the slice.
HUD-01 | Hold tally stick | 1200×120 | Must | 5 | The hold must be readable at a glance.
HUD-02 | Ration selector | 96×96 | Must | 2 | The hold must be readable at a glance.
HUD-03 | Pace selector | 96×96 | Must | 2 | The hold must be readable at a glance.
HUD-04 | Season dial | 320×320 | Must | 3 | The hold must be readable at a glance.
HUD-05 | Watch and day counter | 320×80 | Must | 2 | The hold must be readable at a glance.
HUD-09 | Latitude readout and drift arrow | 96×320, 160×160 | Must | 2 | The hold must be readable at a glance.
ICN-01 | Resource icons | 128×128 (shown at 48–96) | Must | 8 | Hold and ration icons.
ICN-02 | Verb icons | 128×128 | Must | 2 | Hold and ration icons.
ICN-04 | Controller button glyphs | 64×64 | Must | 4 | Hold and ration icons.
UIK-01 | Primary panel 9-slice | 256×256 (margins 48) | Must | 3 | Every screen needs the kit.
UIK-02 | Secondary panel and tooltip 9-slices | 128×128 (margins 24) | Must | 3 | Every screen needs the kit.
UIK-03 | Buttons | 192×64 (margins 24) | Must | 3 | Every screen needs the kit.
UIK-05 | Meter frames and fills | 256×48 | Must | 2 | Every screen needs the kit.
UIK-07 | Dialogue and choice panel | 512×256 (margins 64) | Must | 3 | Every screen needs the kit.
UIK-08 | Toast and notification tag | 256×64 | Must | 1 | Every screen needs the kit.
UIK-09 | Event card frame | 880×760 | Must | 3 | Every screen needs the kit.
CST-01 | Coast strip far: Eriksfjord | 5760×400 | Must | 6 | Eriksfjord departure and landfall at the Strait.
CST-02 | Coast strip near: Eriksfjord | 5760×600 | Must | 8 | Eriksfjord departure and landfall at the Strait.
CST-09 | Coast strip far: The Strait (camp site) | 5760×400 | Must | 6 | Eriksfjord departure and landfall at the Strait.
CST-10 | Coast strip near: The Strait (camp site) | 5760×600 | Must | 8 | Eriksfjord departure and landfall at the Strait.
CST-13 | Landfall beach foreground | 3840×400 | Must | 4 | Eriksfjord departure and landfall at the Strait.
FSH-01 | Underwater cross-section | 1920×1080 | Must | 6 | Hand-line fishing is a slice verb.
FSH-03 | Gunwale and hands with hand line | 1100×500 | Must | 5 | Hand-line fishing is a slice verb.
FSH-04 | Hook, bait, and sinker | 96×96 each | Must | 1 | Hand-line fishing is a slice verb.
FSH-05 | Cod | 320×160 per frame | Must | 8 | Hand-line fishing is a slice verb.
FSH-02 | Current streak particles | 128×32 | Should | 1 | Hand-line fishing is a slice verb.
BLD-01 | Joint workbench close-up | 1920×1080 | Must | 6 | One joint is a slice verb.
BLD-02 | Timber pieces with grain | 1400×400 | Must | 6 | One joint is a slice verb.
BLD-03 | Treenail peg | 120×360 | Must | 1 | One joint is a slice verb.
BLD-04 | Mallet and hands | 700×600 | Must | 4 | One joint is a slice verb.
BLD-05 | Split log state | 1400×400 | Must | 2 | One joint is a slice verb.
BLD-06 | Wood chips and dust | 128×128 per frame | Must | 1 | One joint is a slice verb.
CMP-01 | Camp ground: summer | 3840×1080 | Must | 14 | One camp day.
CMP-06 | Camp far hills layer | 3840×500 | Must | 6 | One camp day.
CMP-07 | Booth (búð) | 420×300 | Must | 6 | One camp day.
CMP-16 | Camp props | up to 300×300 | Must | 10 | One camp day.
CMP-19 | Job markers | 96×128 | Must | 1 | One camp day.
CHR-01 | Crew body rigs | 200×360 bounding | Must | 18 | People at camp.
LOD-02 | Hold cross-section grid | 1600×480 | Must | 5 | The hold grid and tokens.
LOD-03 | Cargo tokens | 96×96 (cattle 144×96) | Must | 5 | The hold grid and tokens.
MAP-01 | Leg map board | 1920×1080 | Must | 12 | The leg chain.
MAP-02 | Region emblems | 160×160 | Must | 7 | The leg chain.
MAP-03 | Route segments | 512×64 tileable | Must | 2 | The leg chain.
EVT-11 | Event: cask breached | 800×450 | Must | 3 | Cask breach is a slice event.
VFX-01 | Soft particle set | 64×64 each | Must | 2 | Splash, smoke, particles.
VFX-02 | Smoke puff sheet | 256×256 per frame | Must | 2 | Splash, smoke, particles.
VFX-03 | Splash sheet | 256×256 per frame | Must | 2 | Splash, smoke, particles.
WFX-07 | Water and wind noise textures | 512×512 | Must | 1 | Shader noise for sea and sail.
MKG-01 | Steam header capsule | 920×430 | Must | 2 | Store page goes up at G1 so wishlists build for a year.
MKG-02 | Steam small capsule | 462×174 | Must | 2 | Store page goes up at G1 so wishlists build for a year.
MKG-03 | Steam main capsule | 1232×706 | Must | 3 | Store page goes up at G1 so wishlists build for a year.
MKG-04 | Steam vertical capsule | 748×896 | Must | 3 | Store page goes up at G1 so wishlists build for a year.
MKG-13 | itch.io cover image | 630×500 | Must | 1 | Store page goes up at G1 so wishlists build for a year.
MKG-05 | Steam page background | 1438×810 | Should | 1 | Store page goes up at G1 so wishlists build for a year.
MKG-14 | itch.io banner and page background | 960×300, 1920×1080 | Should | 2 | Store page goes up at G1 so wishlists build for a year.
| Slice art hours |  |  | 400

## Art Spec
VINLAND · ART
Art spec · the rules every file follows so it drops straight into the Godot build
HOW THIS LIST WORKS
Every asset has an ID, an export size, and a file path. Save your finished PNG at exactly that path inside the project folder and the game picks it up on the next build. Until then the build uses a placeholder drawn at the same size, so nothing waits on art.
Work in phase order. Vertical slice assets come first because the slice (one sea leg, a star fix, a fish, a camp day, one joint) is the go or no-go point of the whole project (gate G1).
The Status column on Asset List is yours. Move each row through Not started, Sketch, In progress, Review, Final, and Imported. The Summary sheet counts hours done and left from it.
Hours are first estimates for one artist painting at a finished-indie standard, including one revision. They exist to plan with; replace them with your own as you learn your pace.
Rows marked Outsource "Yes" are the ones the plan's $18,000 outsource art budget was meant for: ships, UI frames, and sky plates on the plan, plus big background plates here.
Market visitors and their boats, clothing, and goods stay as rough silhouettes until the cultural consultant has reviewed them (Backlog F59, Risk R11). Do not finish them early.
GLOBAL EXPORT RULES
Rule | Specification | Why | Applies to
Base resolution | 1920×1080 game canvas. Godot stretch mode canvas_items, aspect expand. | One art scale for every screen; 4K and 1440p scale up cleanly. | Everything
Steam Deck bleed | Full-screen backgrounds are exported at 1920×1200: the central 1920×1080 is the safe area and 60 px of extra art sits above and below it. | Steam Deck is 16:10. With bleed it shows more art instead of black bars. | Background plates, illustrations used full screen
Source resolution | Paint at 2× (3840×2160 canvas) where you can, then export at the listed size. Keep layered source files (.kra, .psd) in art_source/. | Lets store art and 4K screenshots reuse the same paintings. | Plates, key art, portraits
File format | PNG, 8-bit RGBA, sRGB, straight (not premultiplied) alpha. JPG only where a store asks for it. | Godot imports this without colour shifts. | Everything
Transparency | Clean alpha edges with no halo: matte against the average background colour, never pure white or black. | Prevents bright fringes on sprites over dark sea. | Sprites, overlays
No baked text | No words painted into any asset except the logo. All text is drawn by the game. | Localization and the font size option (F51, F63). | Everything except the logo
Sprite sheets | One animation per file, frames left to right in a single row, every cell the same size, no padding. File name ends in _strip8 (frame count). | Godot imports strips directly into SpriteFrames. | Animated sprites
Frame rate | Creatures and people 12 fps; water, fire, and smoke loops 10 fps; UI 8 fps. Loops must loop without a pop. | Painterly animation reads better on 12 than 24. | Animations
Cutout rigs | Characters that move a lot are cutout rigs: each body part on its own layer, exported as separate PNGs in one folder, with a pivots.txt listing each part's joint point in pixels. | Godot Skeleton2D animates them; one rig serves dozens of animations. | Crew, hunter, visitors
Pivots | Ground-standing sprites: bottom centre. Floating objects: centre. Hanging objects: top centre. Water objects: the waterline. | Code positions sprites by these points. | Sprites
9-slice UI | UI panels are 9-slice: the margin numbers in the Layers column are the unscaled border in pixels on each side. | Panels resize to any text length. | UI kit
Naming | lowercase_with_underscores, starting with the asset ID: sky_01_clear_day.png. Variants add a suffix: _fog, _winter, _s1. | Keeps the build's file paths predictable. | Everything
Sets and variants | Where a row lists several variants, states, or icons, save one PNG per item: the path stem plus a short suffix, e.g. icn_01_resource_icons_timber.png, cmp_08_longhouse_s3.png (stage 3). | The build loads each state by name. | Sprite sets, icon sets, building stages
Folders | art/<category folder>/ as shown in the File path column, inside the Godot project folder. | Matches the paths the build expects. | Everything
SCALE AND LINES THAT MUST MATCH
Measure | Value | Where it is used | Check against
Voyage horizon line | y = 620 (on the 1080 canvas) | All voyage sky plates, sea bands, coast strips | Sea style target
Camp horizon line | y = 540 | Camp skies and camp far hills | Camp style target
Underwater surface line | y = 260 | Hand-line cross-section
Adult at voyage scale | about 110 px tall | Crew on deck, distant figures | Character scale sheet
Adult at camp scale | about 180 px tall | Camp, market, lift | Character scale sheet
Adult at hunt scale | about 340 px tall | Hunter in the stalk scene | Character scale sheet
Cow at camp scale | about 150 px at the shoulder | Livestock | Character scale sheet
Knarr length at voyage scale | about 1,400 px stem to stern | Ship parts canvas 1600×1200 | Sea style target
Smallest readable icon | 48 px on screen (painted at 128) | HUD icons | UI style target at 1280×800
Body text | 22 px minimum at 1080p | All UI | UI style target at 1280×800
STARTING PALETTE · REFINE IT IN THE PALETTE SWATCH SHEET (STY-04)
Name | Hex | Swatch | Use
Labrador slate | #2F4A57 |  | Deep sea, storm water
North Atlantic grey-blue | #5C7C8A |  | Mid sea, overcast sky
Fog white | #DCE3E3 |  | Fog, highlights on water
Midsummer sky | #A9C4D0 |  | Clear-day zenith
Night ink | #141F2B |  | Night sky, deep shadow
Spruce green | #2E4A36 |  | Markland forest, shadows on turf
Turf green | #6E8A4E |  | Summer grass, turf roofs
Lichen yellow | #C8B560 |  | Dye colour, autumn grass
Peat brown | #4A3828 |  | Bog, tarred hull, wet timber
Weathered oak | #8A6D4E |  | Hull planks, UI wood
Birch white | #E8E2D4 |  | Birch bark, UI highlights
Natural wool | #EDE3CC |  | Sail stripes, UI felt
Madder red | #9E3A2E |  | Red cloth, sail stripes, danger
Woad blue | #3F5D85 |  | Dyed clothing
Iron grey | #5E5F5C |  | Tools, blades, rivets
Whale-oil gold | #C9A55A |  | Lamplight, the selected state in UI
UI ink | #1C1915 |  | Text on wood and wool

## Scenes
VINLAND · ART
Scenes · where every asset sits, in draw order from back to front
Scene | Camera | Layers, back to front | Fixed positions | Asset ID prefixes
Voyage | Side-on, static camera; the ship sits left of centre and bobs; the world scrolls past right to left. | 1 sky plate · 2 sun or moon · 3 star field (night) · 4 cloud bands · 5 coast far strip · 6 icebergs far · 7 sea band far · 8 coast near strip · 9 ship (hull, mast, sail, oar, cargo, livestock, crew, damage) · 10 wake · 11 sea band near · 12 drift ice near · 13 weather FX (rain, spray, fog near) · 14 HUD | Horizon y = 620. Ship waterline y = 760, ship centre x = 760. | SKY, CLD, SEA, CST, SHP, WFX, HUD
Star ring | First person, looking north at the sky through the held ring; the view rolls with the ship. | 1 night sky plate · 2 stars and Pole Star · 3 cloud gap overlay · 4 horizon line · 5 false horizon glow · 6 fog sheets · 7 ring · 8 seat glow · 9 hands · 10 result mark | Ring centre at (960, 560). Pole Star placed by code. | SKY, CLD, NAV
Sun board | Top-down at the dial floating in a bowl; the deck below is out of focus. | 1 bowl and blurred deck · 2 dial · 3 gnomon curves · 4 gnomon shadow and tip · 5 peg · 6 overcast dimming · 7 hands (optional) | Dial centre at (960, 540). | NAV
Hand line | Split view: gunwale and surface at the top, underwater below. | 1 underwater cross-section · 2 current particles · 3 fish · 4 hook, bait, sinker · 5 line (code) · 6 fog dimming · 7 gunwale and hands | Surface y = 260. Hands bottom left. | FSH, VFX
Net | Three-quarter view down into shallow water over the side of the boat. | 1 shallow water · 2 fish school · 3 net throw arc · 4 rain overlay · 5 hauled net | Landing area centre (960, 600). | FSH
Hunt | Side-scrolling stalk across a meadow; the camera follows the hunter. | 1 sky plate · 2 far layer · 3 mid layer · 4 animal · 5 hunter · 6 near grass strips · 7 wind streaks · 8 rain overlay | Ground line y = 860. | HNT, WFX
Forage | Top-down close-up of one patch. | 1 patch background (state) · 2 pickups · 3 birds (bird cliff) · 4 reaching hand · 5 basket | Basket bottom right at (1660, 860). | FOR
Joint | Close-up on a trestle, low three-quarter angle. | 1 workbench · 2 timber (wood type) · 3 grain line layer · 4 peg · 5 chips · 6 mallet and hands | Mortise hole at (1010, 520). | BLD
Lift | Side view of the shear legs at the building site or slipway. | 1 camp sky · 2 lift background · 3 lifted timber · 4 rope (code) · 5 hauling crew · 6 slipway surf (slipway only) | Block at (960, 180). | BLD, CHR
Smoke rack | Close-up of the rack and fire from slightly below. | 1 rack background · 2 fish on the rack · 3 fire · 4 smoke column · 5 wind shove FX | Fire centre (960, 900). | BLD
Storm bail | Inside the hold looking aft. | 1 hull interior · 2 bilge water level · 3 lost cask · 4 leak jet · 5 bailing crew · 6 wave over the side · 7 metronome (haptics off) | Water level range y 700–1000. | BAL
Camp | Side-on diorama 3,840 px wide; the camera pans across it. | 1 camp sky · 2 cloud band · 3 far hills · 4 camp ground (season) · 5 buildings and props · 6 livestock and people · 7 snow overlays · 8 weather FX · 9 job markers · 10 HUD | Plot centres (x): palisade 0–300, smithy 420, booths 760 and 1080, smoke rack 1340, longhouse 2000, haystacks 2620, byre 2980, boat shed and slipway 3500. Ground line y = 860. Shore starts x = 3200. | SKY, CMP, ANI, CHR
Market | Same diorama, camera parked on the shore end. | 1 to 4 as Camp · 5 skin boats on the shingle · 6 trade blanket and goods · 7 visitors and crew · 8 market dressing · 9 dialogue panel | Trade blanket centre x = 3050 on the camp ground. | MKT, CMP, CHR
Leg map | Flat view of the carved route board. | 1 map board · 2 route segments · 3 region emblems · 4 weather glyphs · 5 ship token | Node centres: Eriksfjord (1650, 300), Labrador Sea (1350, 380), Helluland (1050, 250), Markland (800, 450), Furðustrandir (620, 620), the Strait (450, 780), Hóp (260, 900). | MAP
Loadout | Upper half the quay, lower half the hold grid. | 1 Eriksfjord quay · 2 hold grid · 3 cargo tokens · 4 outfit cards (outfit choice step) · 5 HUD totals | Hold grid top-left (160, 560); 24 slots in 2 rows of 12, 112 px apart. | LOD
HUD | Overlaid on every play scene. | Top left: watch and day counter. Top centre: toasts. Top right: season dial. Bottom: hold tally stick. Bottom left: ship condition. Bottom right: ration and pace selectors. Camp and market add the fear and goodwill cord top centre. | Hold tally stick at (360, 960); notch 1 at x = 72 on the stick, 44 px apart. | HUD, ICN, UIK
Events and endings | Card over a dimmed scene, or full screen for endings. | 1 dimmed current scene · 2 event card frame · 3 illustration · 4 text and choices (code) | Illustration window at (40, 40) inside the card. | EVT, END, UIK

## Asset List
VINLAND · ART
Asset list · every piece of art in the game, in category order; filter by Phase to see what is needed next
ID | Category | Asset | Description (what to paint) | Used in | Type | Export size (px) | Frames / states | Layers, pivots, and notes | File path | Phase needed | Priority | Backlog | Outsource? | Est. hours | Status | Your notes
STY-01 | Style targets | Sea style target paintover | Finished-quality frame of the voyage view at golden hour: knarr under full sail on a long swell, Markland forest on the horizon, crew silhouettes on deck. Sets brushwork, edge softness, value structure, and how much detail a 1080p frame carries. Every sea, sky, and ship asset is judged against it. | Voyage | Paintover | 1920×1080 | 1 | Paint as separate layers in the voyage layer order (see Scenes) so it can be cut into real assets later. Keep the PSD/KRA. | art_source/style/sty_01_sea_style_target_paintover.png | Preproduction | Must | F44 | No | 10 | Not started
STY-02 | Style targets | Camp style target paintover | Summer camp on the Strait shore: two booths raised, longhouse frame half up, bull tethered, smoke rack lit, knarr drawn up on the shingle. Sets the look of turf, timber, wool, and people at camp scale. | Camp | Paintover | 1920×1080 | 1 | Layered in the camp layer order. Character scale is set here: an adult is about 180 px tall at camp scale. | art_source/style/sty_02_camp_style_target_paintover.png | Preproduction | Must | F44 | No | 10 | Not started
STY-03 | Style targets | UI style target paintover | One HUD frame over the voyage view: hold tally stick, ration and pace selectors, season dial, one dialogue panel and two buttons. Wood, wool, and a ring; no chrome, no glow, no gradients that read as plastic. | All | Paintover | 1920×1080 | 1 | Proves legibility of 22 px body text on painted wood. Check at 1280×800 (Steam Deck) as well. | art_source/style/sty_03_ui_style_target_paintover.png | Preproduction | Must | F44 | No | 6 | Not started
STY-04 | Style targets | Palette swatch sheet | The master palette: 6 sea and sky blues, 5 turf and spruce greens, 4 wool creams, madder red (red cloth), iron grey, birch white, peat brown, whale-oil gold, plus the UI ink colour. Each with its hex code written under it. | All | Reference sheet | 1024×512 | 1 | Also export as a .gpl (Krita/GIMP) or .ase (Photoshop) palette file beside the PNG. Starting values are on the Art Spec sheet. | art_source/style/sty_04_palette_swatch_sheet.png | Preproduction | Must | F44 | No | 2 | Not started
STY-05 | Style targets | Character scale and proportion sheet | Line-up of the human body types (2 sexes × 3 builds), a child, a cow, a sheep, and the knarr hull, all at camp scale, with a 1 m measuring stick. Adults are slightly stylised (head about 1/7 of height) so poses read at small size. | All | Reference sheet | 1920×1080 | 1 | Every character and animal asset is drawn to this sheet. | art_source/style/sty_05_character_scale_and_proportion_sheet.png | Preproduction | Must | F44 | No | 4 | Not started
STY-06 | Style targets | Greyscale readability test | The sea and camp targets converted to greyscale, with the ship, people, and interactive objects checked for contrast against the background. Annotate any spot where the player could lose the ship or the cursor. | All | Reference sheet | 1920×1080 | 2 | Not shipped. Keep for the art bible. | art_source/style/sty_06_greyscale_readability_test.png | Preproduction | Should | F44 | No | 1 | Not started
SKY-01 | Sky plates and celestial | Sky plate: clear day | High-latitude summer day: pale cold blue at the zenith fading to a hazy, almost white horizon. A few high cirrus streaks only. Bright but never saturated. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Static, rearmost layer. Horizon line at y = 620 for all voyage sky plates so they swap without shifting. | res://art/sky/sky_01_sky_plate_clear_day.png | Vertical slice | Must | F02 | Yes | 5 | Not started
SKY-02 | Sky plates and celestial | Sky plate: overcast | Flat grey-blue cloud deck with slightly darker undersides. The sun is a faint brighter patch only. Reads as no sun board today. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. | res://art/sky/sky_02_sky_plate_overcast.png | Production | Must | F09 | Yes | 4 | Not started
SKY-03 | Sky plates and celestial | Sky plate: fog | Near-white luminous fog that eats the horizon entirely; the sun is a pale disc that may or may not be there. Feels close and quiet. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Pairs with the fog sheet layers. Horizon is implied, not drawn. | res://art/sky/sky_03_sky_plate_fog.png | Vertical slice | Must | F09 | Yes | 4 | Not started
SKY-04 | Sky plates and celestial | Sky plate: low cloud | Ragged scud racing low over the sea under a higher grey layer, with breaks of pale light. Used for the low-cloud weather card. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. | res://art/sky/sky_04_sky_plate_low_cloud.png | Production | Must | F09 | Yes | 4 | Not started
SKY-05 | Sky plates and celestial | Sky plate: dawn | Cold peach and lilac band along the horizon under a deep blue sky; last stars fading in the upper third. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. | res://art/sky/sky_05_sky_plate_dawn.png | Production | Should | F35 | Yes | 4 | Not started
SKY-06 | Sky plates and celestial | Sky plate: summer twilight | The short northern night: the sky never fully darkens, a lingering amber glow under the north horizon, a few bright stars. This is the hardest night for the star ring. | Voyage, Star ring | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. Reused behind the star ring at reduced brightness. | res://art/sky/sky_06_sky_plate_summer_twilight.png | Vertical slice | Must | F03 | Yes | 5 | Not started
SKY-07 | Sky plates and celestial | Sky plate: clear night | Deep blue-black night with a faint Milky Way and a hint of horizon light. Clean, readable star field for a clean fix. | Voyage, Star ring | Background plate | 1920×1200 (1080 safe) | 1 | Stars are separate sprites; paint only the gradient and Milky Way haze here. | res://art/sky/sky_07_sky_plate_clear_night.png | Vertical slice | Must | F03 | Yes | 5 | Not started
SKY-08 | Sky plates and celestial | Sky plate: clouded night | Night sky mostly covered by dark cloud with two or three ragged gaps. The difficulty of the ring comes from these gaps. | Voyage, Star ring | Background plate | 1920×1200 (1080 safe) | 1 | Cloud gaps are also delivered as separate overlay sprites so the code can move them. | res://art/sky/sky_08_sky_plate_clouded_night.png | Vertical slice | Must | F03 | Yes | 4 | Not started
SKY-09 | Sky plates and celestial | Sky plate: storm | Bruised slate cloud wall, rain curtains hanging from it, a lighter seam at the horizon. Oppressive, low contrast. | Voyage, Storm bail | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. | res://art/sky/sky_09_sky_plate_storm.png | Production | Must | F10 | Yes | 5 | Not started
SKY-10 | Sky plates and celestial | Sky plate: autumn grey | Heavier, colder overcast with a long low sun glare under the cloud edge. The return voyage bias: everything a step darker and colder than summer. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Horizon at y = 620. | res://art/sky/sky_10_sky_plate_autumn_grey.png | Alpha | Must | F24 | Yes | 4 | Not started
SKY-11 | Sky plates and celestial | Sky plate: aurora night | Autumn night with a green aurora curtain low in the north. Rare event sky on the return voyage; a moment of beauty, not a gameplay signal. | Voyage | Background plate | 1920×1200 (1080 safe) | 1 | Aurora painted on its own layer so it can be faded in. | res://art/sky/sky_11_sky_plate_aurora_night.png | Alpha | Could | F24 | Yes | 5 | Not started
SKY-12 | Sky plates and celestial | Sky plate: winter camp | Pale, low winter sky with a sun barely above the treeline, long cold shadows implied. Used over the camp in winter. | Camp | Background plate | 1920×1200 (1080 safe) | 1 | Camp horizon line at y = 540 (camp plates use their own horizon). | res://art/sky/sky_12_sky_plate_winter_camp.png | Production | Must | F47 | Yes | 4 | Not started
SKY-13 | Sky plates and celestial | Sky plate: camp summer and autumn | Two camp skies: a bright summer afternoon and a hazy autumn evening, matched to the camp horizon. | Camp, Market | Background plate | 1920×1200 (1080 safe) | 2 variants | Camp horizon at y = 540. | res://art/sky/sky_13_sky_plate_camp_summer_and_autumn.png | Vertical slice | Must | F06 | Yes | 7 | Not started
SKY-14 | Sky plates and celestial | Sun disc with glow | Soft sun disc with a warm bloom; a second, dimmer version for haze and fog. | Voyage, Sun board | Sprite | 256×256 | 2 variants | Centre pivot. Additive blend friendly: paint on transparent black-free alpha. | res://art/sky/sky_14_sun_disc_with_glow.png | Vertical slice | Must | F04 | No | 1 | Not started
SKY-15 | Sky plates and celestial | Moon phases | Eight moon phases, pale and slightly textured, small enough not to compete with the Pole Star. | Voyage, Star ring | Sprite sheet | 128×128 per frame | 8 frames | Horizontal strip, 1024×128. Centre pivot. | res://art/sky/sky_15_moon_phases_strip.png | Production | Should | F35 | No | 2 | Not started
SKY-16 | Sky plates and celestial | Voyage night star field | Sparse star field for the voyage view: only the brightest marks, uneven, with a few faint ones. Not a planetarium. | Voyage | Overlay | 1920×1080 | 1 | Transparent PNG over the night sky plates. | res://art/sky/sky_16_voyage_night_star_field.png | Vertical slice | Must | F02 | No | 2 | Not started
CLD-01 | Clouds and fog layers | Cloud band: fair weather | Scattered cumulus and streaks along the upper sky, painted to tile seamlessly left-right. Drifts slowly with the wind. | Voyage, Camp | Tileable layer | 3840×540 | 1 | Horizontal tile; transparent. Top-anchored. | res://art/clouds/cld_01_cloud_band_fair_weather.png | Vertical slice | Must | F02 | Yes | 4 | Not started
CLD-02 | Clouds and fog layers | Cloud band: overcast underside | Dark, rolling undersides of a cloud deck that tile horizontally; gives the overcast plate movement. | Voyage | Tileable layer | 3840×540 | 1 | Horizontal tile; transparent. | res://art/clouds/cld_02_cloud_band_overcast_underside.png | Production | Must | F09 | Yes | 3 | Not started
CLD-03 | Clouds and fog layers | Cloud band: low scud | Torn, fast-moving fragments at mid height, semi-transparent. | Voyage | Tileable layer | 3840×400 | 1 | Horizontal tile; scrolls faster than the other cloud layers. | res://art/clouds/cld_03_cloud_band_low_scud.png | Production | Must | F09 | Yes | 3 | Not started
CLD-04 | Clouds and fog layers | Cloud wall: storm | Heavy storm wall with rain shafts hanging from it, tileable, sitting just above the horizon. | Voyage | Tileable layer | 3840×600 | 1 | Horizontal tile; transparent. | res://art/clouds/cld_04_cloud_wall_storm.png | Production | Must | F10 | Yes | 4 | Not started
CLD-05 | Clouds and fog layers | Fog sheets | Three layers of soft fog banks at different densities (far, mid, near) that tile horizontally and slide past each other. | Voyage, Star ring, Hand line | Tileable layer | 3840×1080 | 3 layers | Transparent, soft-edged. The near layer sits in front of the ship. | res://art/clouds/cld_05_fog_sheets.png | Vertical slice | Must | F09 | No | 4 | Not started
CLD-06 | Clouds and fog layers | Cloud gap overlays for the ring | Four cloud-cover overlays for the star ring view, each with one or two holes where stars can be seen. The holes are where the fix can be made. | Star ring | Overlay | 1920×1080 | 4 variants | Transparent. Code moves and fades them; keep hole edges soft. | res://art/clouds/cld_06_cloud_gap_overlays_for_the_ring.png | Vertical slice | Must | F03 | No | 4 | Not started
CLD-07 | Clouds and fog layers | False horizon glow | A band of misleading light near the horizon in fog, which the player might mistake for the real horizon. | Star ring | Overlay | 1920×300 | 1 | Additive blend, transparent. Placed by code at a false height. | res://art/clouds/cld_07_false_horizon_glow.png | Vertical slice | Must | F03 | No | 1 | Not started
SEA-01 | Sea, ice and wildlife | Sea band far: calm | Distant sea surface in calm: glassy, with gentle long reflections. Tiles horizontally. | Voyage | Tileable layer | 3840×300 | 1 | Top edge meets horizon (y = 620). Scroll speed slowest. | res://art/sea/sea_01_sea_band_far_calm.png | Vertical slice | Must | F02 | Yes | 3 | Not started
SEA-02 | Sea, ice and wildlife | Sea band far: swell | Distant sea with a long Atlantic swell and occasional whitecaps. | Voyage | Tileable layer | 3840×300 | 1 | As above. | res://art/sea/sea_02_sea_band_far_swell.png | Vertical slice | Must | F02 | Yes | 3 | Not started
SEA-03 | Sea, ice and wildlife | Sea band far: beam sea | Steep cross seas running across the ship's course, confused and choppy. | Voyage | Tileable layer | 3840×300 | 1 | As above. | res://art/sea/sea_03_sea_band_far_beam_sea.png | Production | Must | F09 | Yes | 3 | Not started
SEA-04 | Sea, ice and wildlife | Sea band far: gale and storm | Two states: a following gale with long streaked crests, and a storm sea with breaking tops and spindrift. | Voyage | Tileable layer | 3840×300 | 2 variants | As above. | res://art/sea/sea_04_sea_band_far_gale_and_storm.png | Production | Must | F10 | Yes | 6 | Not started
SEA-05 | Sea, ice and wildlife | Sea band near with foam | Foreground water in front of the ship for each sea state (calm, swell, beam, gale, storm). Darker, larger shapes, foam lines. | Voyage | Tileable layer | 3840×400 | 5 variants | Bottom-anchored, in front of the ship. Ship bobbing is done in code. | res://art/sea/sea_05_sea_band_near_with_foam.png | Vertical slice | Must | F02 | Yes | 12 | Not started
SEA-06 | Sea, ice and wildlife | Bow wake and hull foam | Foam curl at the bow and a trailing wake that loops, for when the ship is under way. | Voyage | Sprite sheet | 512×256 per frame | 8 frames | Horizontal strip. Pivot at the waterline. | res://art/sea/sea_06_bow_wake_and_hull_foam_strip.png | Vertical slice | Must | F02 | No | 3 | Not started
SEA-07 | Sea, ice and wildlife | Drift ice floes | Six loose floes of different sizes, flat-topped, with blue-green underwater shelves visible. | Voyage | Sprite set | up to 512×200 | 6 variants | Bottom pivot at waterline. Code scatters and scrolls them. | res://art/sea/sea_07_drift_ice_floes.png | Production | Must | F09 | No | 4 | Not started
SEA-08 | Sea, ice and wildlife | Icebergs | Three icebergs (small, medium, tabular) for the Labrador Sea and Helluland legs. | Voyage | Sprite set | up to 900×500 | 3 variants | Bottom pivot at waterline; include a separate reflection sprite. | res://art/sea/sea_08_icebergs.png | Production | Should | F11 | No | 4 | Not started
SEA-09 | Sea, ice and wildlife | Whale back and spout | A whale surfacing and blowing near the ship, then sounding. Ambient life on open water. | Voyage | Sprite sheet | 512×256 per frame | 12 frames | Horizontal strip. Plays rarely. | res://art/sea/sea_09_whale_back_and_spout_strip.png | Production | Could | — | No | 4 | Not started
SEA-10 | Sea, ice and wildlife | Seabird flock | Small flock of gulls and fulmars banking over the sea; signals land is near. | Voyage, Camp | Sprite sheet | 256×128 per frame | 8 frames | Loop. Used as a landfall hint. | res://art/sea/sea_10_seabird_flock_strip.png | Production | Should | F11 | No | 2 | Not started
CST-01 | Coasts by leg | Coast strip far: Eriksfjord | Green, steep fjord sides with farm fields and turf houses of Brattahlíð, glacier ice glinting at the fjord head, small icebergs in the water. Home: warm in colour even when cold. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_01_coast_strip_far_eriksfjord.png | Vertical slice | Must | F02 | Yes | 6 | Not started
CST-02 | Coasts by leg | Coast strip near: Eriksfjord | Green, steep fjord sides with farm fields and turf houses of Brattahlíð, glacier ice glinting at the fjord head, small icebergs in the water. Home: warm in colour even when cold. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_02_coast_strip_near_eriksfjord.png | Vertical slice | Must | F02 | Yes | 8 | Not started
CST-03 | Coasts by leg | Coast strip far: Helluland | Flat, bare stone slabs and grey rock running to the sea (the sagas' "land of flat stones"), with snow patches and no trees. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_03_coast_strip_far_helluland.png | Production | Must | F11 | Yes | 6 | Not started
CST-04 | Coasts by leg | Coast strip near: Helluland | Flat, bare stone slabs and grey rock running to the sea (the sagas' "land of flat stones"), with snow patches and no trees. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_04_coast_strip_near_helluland.png | Production | Must | F11 | Yes | 8 | Not started
CST-05 | Coasts by leg | Coast strip far: Markland | Low coast of dense dark spruce forest right to the shoreline (the "land of forest"). The timber the whole game is about. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_05_coast_strip_far_markland.png | Production | Must | F11 | Yes | 6 | Not started
CST-06 | Coasts by leg | Coast strip near: Markland | Low coast of dense dark spruce forest right to the shoreline (the "land of forest"). The timber the whole game is about. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_06_coast_strip_near_markland.png | Production | Must | F11 | Yes | 8 | Not started
CST-07 | Coasts by leg | Coast strip far: Furðustrandir | Very long pale sand beaches backed by low dunes and scrub (the "wonder strands"). The coast seems to go on forever. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_07_coast_strip_far_furdustrandir.png | Production | Must | F11 | Yes | 6 | Not started
CST-08 | Coasts by leg | Coast strip near: Furðustrandir | Very long pale sand beaches backed by low dunes and scrub (the "wonder strands"). The coast seems to go on forever. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_08_coast_strip_near_furdustrandir.png | Production | Must | F11 | Yes | 8 | Not started
CST-09 | Coasts by leg | Coast strip far: The Strait (camp site) | Grassy marine terrace with a bog and a brook running to a shallow shingle shore; low hills behind. The colony site. Base this on the setting of L'Anse aux Meadows, Newfoundland. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_09_coast_strip_far_the_strait.png | Vertical slice | Must | F02 | Yes | 6 | Not started
CST-10 | Coasts by leg | Coast strip near: The Strait (camp site) | Grassy marine terrace with a bog and a brook running to a shallow shingle shore; low hills behind. The colony site. Base this on the setting of L'Anse aux Meadows, Newfoundland. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_10_coast_strip_near_the_strait.png | Vertical slice | Must | F02 | Yes | 8 | Not started
CST-11 | Coasts by leg | Coast strip far: Hóp | A lagoon behind a sandbar at a river mouth, lush lowland with tall grass and vines. Warmer light than anywhere else in the game. Far layer: low-contrast silhouette near the horizon. | Voyage | Scrolling strip | 5760×400 | 1 | Bottom edge sits on the horizon (y = 620). Not tileable; scrolls past once per leg. Transparent sky. | res://art/coast/cst_11_coast_strip_far_hop.png | Alpha | Should | F27 | Yes | 6 | Not started
CST-12 | Coasts by leg | Coast strip near: Hóp | A lagoon behind a sandbar at a river mouth, lush lowland with tall grass and vines. Warmer light than anywhere else in the game. Near layer: closer headlands with readable detail, used as the ship approaches landfall. | Voyage | Scrolling strip | 5760×600 | 1 | Bottom-anchored behind the near sea band. | res://art/coast/cst_12_coast_strip_near_hop.png | Alpha | Should | F27 | Yes | 8 | Not started
CST-13 | Coasts by leg | Landfall beach foreground | Shingle and boulder beach with kelp wrack, seen up close as the knarr is run ashore; used for every landing. | Voyage, Camp | Foreground layer | 3840×400 | 1 | Bottom-anchored. Tint is varied per leg in code. | res://art/coast/cst_13_landfall_beach_foreground.png | Vertical slice | Must | F02 | Yes | 4 | Not started
SHP-01 | The knarr and other vessels | Knarr hull (side view) | A deep-bellied Norse cargo ship seen side-on, bow to the right: overlapping clinker strakes, a high curved stem and stern, a half-deck fore and aft with an open hold amidships. Oak and pine, tarred, weathered. This is the player's home for half the game. | Voyage | Sprite (cutout part) | 1400×560 | 1 | Pivot at the centre of the waterline. The hull is the root of the ship rig; all other ship parts are separate layers aligned to the same 1600×1200 canvas. | res://art/ship/shp_01_knarr_hull.png | Vertical slice | Must | F02 | Yes | 12 | Not started
SHP-02 | The knarr and other vessels | Mast and yard | Single pine mast with a yard, stays and shrouds as thin lines. | Voyage | Sprite (cutout part) | 400×900 | 1 | Separate layer on the shared ship canvas. Pivot at the mast step. | res://art/ship/shp_02_mast_and_yard.png | Vertical slice | Must | F02 | Yes | 2 | Not started
SHP-03 | The knarr and other vessels | Sail states | Square woollen sail in three states: furled on the yard, reefed, full and drawing. Woven in wide madder-red and natural-wool stripes, slightly patched. | Voyage | Sprite set | 900×800 | 3 states | Same anchor point for each state so they swap cleanly. Keep sail edges crisp for a shader billow. | res://art/ship/shp_03_sail_states.png | Vertical slice | Must | F38 | Yes | 6 | Not started
SHP-04 | The knarr and other vessels | Torn sail overlay | Rips and a flogging loose corner on the full sail. | Voyage | Overlay | 900×800 | 2 levels | Laid over the full sail. Ship condition system. | res://art/ship/shp_04_torn_sail_overlay.png | Production | Must | F45 | No | 2 | Not started
SHP-05 | The knarr and other vessels | Steering oar | The side rudder on the starboard quarter with its tiller, held by the helmsman. | Voyage | Sprite (cutout part) | 160×520 | 1 | Pivot at the hull fixing point so code can swing it. | res://art/ship/shp_05_steering_oar.png | Vertical slice | Must | F02 | No | 1 | Not started
SHP-06 | The knarr and other vessels | Oars out | A bank of oars run out through the oar ports for a calm day, in two stroke positions. | Voyage | Sprite set | 1200×300 | 2 frames | For the calm-oars state. | res://art/ship/shp_06_oars_out.png | Production | Should | F09 | No | 3 | Not started
SHP-07 | The knarr and other vessels | Hull damage overlays | A sprung strake leaking in three levels (a seep, a spurt, a gash), and patch repairs once fixed. | Voyage, Storm bail | Overlay | 1400×560 | 4 states | Aligned to the hull canvas. | res://art/ship/shp_07_hull_damage_overlays.png | Production | Must | F45 | No | 3 | Not started
SHP-08 | The knarr and other vessels | Deck cargo stack states | What the open hold shows from outside: hide-covered bundles and casks rising from almost empty to over-full and lashed high. Five states that follow the hold tally. | Voyage | Sprite set | 700×260 | 5 states | Aligned to the hull canvas; sits in the open hold amidships. Swapped by hold fill. | res://art/ship/shp_08_deck_cargo_stack_states.png | Vertical slice | Must | F01 | No | 5 | Not started
SHP-09 | The knarr and other vessels | Livestock on deck | A small pen amidships with a cow and a bull standing, and sheep pressed together, seen side-on above the gunwale. Two count states (few, many). | Voyage | Sprite set | 500×240 | 2 states | Aligned to the hull canvas. | res://art/ship/shp_09_livestock_on_deck.png | Production | Must | F16 | No | 3 | Not started
SHP-10 | The knarr and other vessels | Crew on deck | Small silhouette figures at fixed posts: helmsman at the steering oar, a lookout at the bow, four midships figures that can row, bail, or sit. Each post in idle and working poses. | Voyage | Sprite set | 80×140 each | 6 posts × 2 poses | Code toggles figures by crew count and task. Painted at voyage scale (about 110 px tall). | res://art/ship/shp_10_crew_on_deck.png | Vertical slice | Must | F02 | No | 6 | Not started
SHP-11 | The knarr and other vessels | Second knarr (distant) | The relief ship or a second hull seen far off on the horizon: sail up, small, catching light. | Voyage, Camp | Sprite | 400×300 | 1 | Bottom pivot at the waterline. | res://art/ship/shp_11_second_knarr.png | Alpha | Must | F26 | Yes | 2 | Not started
SHP-12 | The knarr and other vessels | Knarr on the slipway | The ship hauled up on log rollers at the camp, tilted, without its mast stepped; with a variant under repair (strakes off, ribs showing). | Camp | Sprite set | 1400×700 | 2 states | Camp scale. Bottom pivot. | res://art/ship/shp_12_knarr_on_the_slipway.png | Production | Must | F18 | Yes | 6 | Not started
SHP-13 | The knarr and other vessels | Ship token for the map | A tiny stylised knarr seen side-on, carved-wood look, used to mark position on the leg map. | Leg map | Icon | 128×128 | 1 | Centre pivot. | res://art/ship/shp_13_ship_token_for_the_map.png | Vertical slice | Must | F11 | No | 1 | Not started
WFX-01 | Weather and water effects | Rain streak textures | Three rain densities as tileable streak textures (drizzle, rain, downpour), slanted for wind. | Voyage, Camp, Hunt | Tileable texture | 1024×1024 | 3 variants | Used by a scrolling shader. Grey-white on transparent. | res://art/weather_fx/wfx_01_rain_streak_textures.png | Production | Must | F09 | No | 2 | Not started
WFX-02 | Weather and water effects | Snow and sleet textures | Soft snowflake field and wet sleet streaks, tileable. | Camp, Voyage | Tileable texture | 1024×1024 | 2 variants | As above. | res://art/weather_fx/wfx_02_snow_and_sleet_textures.png | Production | Must | F47 | No | 2 | Not started
WFX-03 | Weather and water effects | Spray burst | White water exploding off the bow when it drives into a wave. | Voyage | Sprite sheet | 512×512 per frame | 10 frames | Horizontal strip, centre-bottom pivot. | res://art/weather_fx/wfx_03_spray_burst_strip.png | Production | Must | F10 | No | 3 | Not started
WFX-04 | Weather and water effects | Green water over the gunwale | A solid wave breaking into the hold, seen from outside. | Voyage | Sprite sheet | 768×384 per frame | 10 frames | Plays during storm cards. | res://art/weather_fx/wfx_04_green_water_over_the_gunwale_strip.png | Production | Must | F10 | No | 4 | Not started
WFX-05 | Weather and water effects | Lightning bolts | Two branching bolts from cloud to sea, plus a full-screen flash tint frame. | Voyage | Sprite set | 600×1080 | 2 bolts + 1 flash | Additive. | res://art/weather_fx/wfx_05_lightning_bolts.png | Production | Should | F10 | No | 1 | Not started
WFX-06 | Weather and water effects | Wind streaks | Long faint streaks showing wind direction and strength over the sea. | Voyage, Hunt | Sprite set | 512×64 | 4 variants | Additive, low opacity. Also a visual twin for haptic wind cues. | res://art/weather_fx/wfx_06_wind_streaks.png | Production | Must | F32 | No | 1 | Not started
WFX-07 | Weather and water effects | Water and wind noise textures | Tileable greyscale noise maps for the sea shimmer, sail billow, and grass sway shaders. | All | Shader texture | 512×512 | 3 maps | Seamless in both directions. Can be generated. | res://art/weather_fx/wfx_07_water_and_wind_noise_textures.png | Vertical slice | Must | F02 | No | 1 | Not started
NAV-01 | Navigation mini-games (star ring, sun board) | Star ring instrument | The game's signature object: a wooden sighting ring about a hand-span across, carved with notches and worn smooth by thumbs, with a sighting bead on a cord. Seen close, held up against the night sky. It must feel like a real tool someone made. | Star ring | Sprite (cutout part) | 900×900 | 1 | Centre pivot. Transparent centre so the sky shows through. The most-looked-at asset in the game; give it the most care. | res://art/navigate/nav_01_star_ring_instrument.png | Vertical slice | Must | F03 | No | 10 | Not started
NAV-02 | Navigation mini-games (star ring, sun board) | Ring notch highlight and seat glow | The notch on the ring that lights up when the Pole Star is seated, plus a soft ring-rim brightening. This is the visual twin of the haptic seat cue. | Star ring | Overlay | 900×900 | 3 strengths | Additive; aligned to the ring. | res://art/navigate/nav_02_ring_notch_highlight_and_seat_glow.png | Vertical slice | Must | F32 | No | 2 | Not started
NAV-03 | Navigation mini-games (star ring, sun board) | Hands holding the ring | Two weathered hands in wool sleeve cuffs gripping the ring from below, left and right separately. | Star ring | Sprite (cutout part) | 600×700 each | 2 parts | Pivots at the wrists so they can follow the ring. | res://art/navigate/nav_03_hands_holding_the_ring.png | Vertical slice | Must | F03 | No | 4 | Not started
NAV-04 | Navigation mini-games (star ring, sun board) | Pole Star and star marks | The Pole Star as a small, clear, slightly larger glint, plus 12 star sprites of different brightness for the guide marks around it (the Plough, Cassiopeia). | Star ring | Sprite set | 64×64 each | 13 sprites | Centre pivot. Code places them; each needs a soft twinkle variant (2 frames). | res://art/navigate/nav_04_pole_star_and_star_marks.png | Vertical slice | Must | F03 | No | 2 | Not started
NAV-05 | Navigation mini-games (star ring, sun board) | Ring horizon line | A dark sea horizon seen through the ring, with a faint lighter sky edge, which the ring is levelled against. | Star ring | Overlay | 1920×200 | 2 variants (clear, hazy) | Code moves it with ship roll. | res://art/navigate/nav_05_ring_horizon_line.png | Vertical slice | Must | F03 | No | 1 | Not started
NAV-06 | Navigation mini-games (star ring, sun board) | Fix result marks | Three carved-wood result plaques: clean fix, partial fix, no fix. Small, readable, no text needed (text is in the line below). | Star ring, Sun board | Icon set | 256×256 | 3 icons | Centre pivot. | res://art/navigate/nav_06_fix_result_marks.png | Vertical slice | Must | F03 | No | 2 | Not started
NAV-07 | Navigation mini-games (star ring, sun board) | Sun board dial | A round wooden bearing dial seen from above, floated in a bowl of water to stay level, with a central gnomon pin and incised compass marks. Based on the Uunartoq disc find. | Sun board | Sprite (cutout part) | 900×900 | 1 | Centre pivot; rotates in code. | res://art/navigate/nav_07_sun_board_dial.png | Vertical slice | Must | F04 | No | 8 | Not started
NAV-08 | Navigation mini-games (star ring, sun board) | Gnomon curve inlays | The scratched curves on the board that the shadow tip should touch at the right latitude; three curves (home, Markland, Vinland latitude). | Sun board | Overlay | 900×900 | 3 overlays | Aligned to the dial. | res://art/navigate/nav_08_gnomon_curve_inlays.png | Vertical slice | Must | F04 | No | 2 | Not started
NAV-09 | Navigation mini-games (star ring, sun board) | Gnomon shadow and tip glint | The gnomon's shadow as a soft stretched shape with a brighter tip glint (the visual twin of the haptic hum). | Sun board | Sprite set | 64×512 | 2 parts | Pivot at the gnomon base; code rotates and stretches it. | res://art/navigate/nav_09_gnomon_shadow_and_tip_glint.png | Vertical slice | Must | F04 | No | 1 | Not started
NAV-10 | Navigation mini-games (star ring, sun board) | Sun board peg and water bowl | A small wooden marker peg, and the shallow wooden bowl of water the board floats in, seen from above with the deck blurred below. | Sun board | Sprite set | 1400×1000 bowl, 64×128 peg | 2 parts | Bowl is the backdrop; peg is moved by the right stick. | res://art/navigate/nav_10_sun_board_peg_and_water_bowl.png | Vertical slice | Must | F04 | No | 4 | Not started
FSH-01 | Fishing (hand line, net) | Underwater cross-section | Split view for the hand line: the boat gunwale and sea surface in the top quarter, then cold green-blue coastal water with kelp, rocks, and a gravel bottom fading into darkness. | Hand line | Background plate | 1920×1200 (1080 safe) | 2 variants (clear, fog-dimmed) | Surface line at y = 260. Static. | res://art/fish/fsh_01_underwater_cross_section.png | Vertical slice | Must | F05 | Yes | 6 | Not started
FSH-02 | Fishing (hand line, net) | Current streak particles | Faint sediment and bubble streaks showing current direction underwater. | Hand line | Sprite set | 128×32 | 4 variants | Additive, low opacity. | res://art/fish/fsh_02_current_streak_particles.png | Vertical slice | Should | F05 | No | 1 | Not started
FSH-03 | Fishing (hand line, net) | Gunwale and hands with hand line | Foreground: the boat's edge with two hands paying out a line from a wooden winding frame. | Hand line | Sprite (cutout part) | 1100×500 | 3 poses (hold, pay out, set) | Bottom-left anchor. The line itself is drawn in code. | res://art/fish/fsh_03_gunwale_and_hands_with_hand_line.png | Vertical slice | Must | F05 | No | 5 | Not started
FSH-04 | Fishing (hand line, net) | Hook, bait, and sinker | Bone or iron hook with a scrap of bait, and a grooved stone sinker. | Hand line | Sprite set | 96×96 each | 3 sprites | Pivot at the line tie point. | res://art/fish/fsh_04_hook_bait_and_sinker.png | Vertical slice | Must | F05 | No | 1 | Not started
FSH-05 | Fishing (hand line, net) | Cod | Atlantic cod: swim cycle, nose-in to the bait, the two-beat bite, hooked struggle, and landed on deck. | Hand line, Net | Sprite sheet | 320×160 per frame | swim 8, bite 4, struggle 6, landed 2 | One sheet per animation, horizontal strips. Centre pivot. | res://art/fish/fsh_05_cod_strip.png | Vertical slice | Must | F05 | No | 8 | Not started
FSH-06 | Fishing (hand line, net) | Salmon and Arctic char | River-run salmon and a smaller char, each with swim and hooked frames, for river-mouth fishing. | Hand line, Net | Sprite sheet | 320×140 per frame | swim 8, struggle 6 each | As above. | res://art/fish/fsh_06_salmon_and_arctic_char_strip.png | Production | Must | F14 | No | 8 | Not started
FSH-07 | Fishing (hand line, net) | Halibut | A big flatfish rising off the bottom; a heavy, slow struggle. The rare catch. | Hand line | Sprite sheet | 400×240 per frame | swim 6, struggle 6 | As above. | res://art/fish/fsh_07_halibut_strip.png | Production | Could | F05 | No | 5 | Not started
FSH-08 | Fishing (hand line, net) | Fish school | A loose school of capelin or herring that tightens and turns, seen from above in shallow water; it darkens the surface when under the boat. | Net | Sprite sheet | 512×512 per frame | 12 frames | Loop. Also the visual twin of the haptic net weight. | res://art/fish/fsh_08_fish_school_strip.png | Production | Must | F14 | No | 5 | Not started
FSH-09 | Fishing (hand line, net) | Shallow water from above | Top-down three-quarter view over the side of the boat into shallow water: rippled surface, sandy bottom patches, kelp. | Net | Background plate | 1920×1200 (1080 safe) | 2 variants (clear, rain) | Static. | res://art/fish/fsh_09_shallow_water_from_above.png | Production | Must | F14 | Yes | 5 | Not started
FSH-10 | Fishing (hand line, net) | Net throw arc | A cast net opening in the air and spreading as it lands, then sinking. | Net | Sprite sheet | 640×640 per frame | 12 frames | Centre pivot at the landing point. | res://art/fish/fsh_10_net_throw_arc_strip.png | Production | Must | F14 | No | 6 | Not started
FSH-11 | Fishing (hand line, net) | Net hauled: empty and full | The net drawn back to the gunwale: hanging empty and dripping, or bulging with silver fish. | Net | Sprite set | 600×500 | 2 states | Bottom pivot. | res://art/fish/fsh_11_net_hauled_empty_and_full.png | Production | Must | F14 | No | 3 | Not started
HNT-01 | Hunting (stalk and loose) | Stalk scene: far layer | Distant low hills, scattered spruce, and open sky over a wide meadow, low contrast. | Hunt | Parallax layer | 3840×700 | 1 | Horizontal scroll at 0.2× camera speed. | res://art/hunt/hnt_01_stalk_scene_far_layer.png | Production | Must | F12 | Yes | 5 | Not started
HNT-02 | Hunting (stalk and loose) | Stalk scene: mid layer | Mid-distance meadow with bushes, boulders, and a stand of trees where the animal grazes. | Hunt | Parallax layer | 3840×800 | 1 | Scroll at 0.5×. | res://art/hunt/hnt_02_stalk_scene_mid_layer.png | Production | Must | F12 | Yes | 6 | Not started
HNT-03 | Hunting (stalk and loose) | Stalk scene: near grass strips | Three strips of tall grass and sedge in the foreground that the hunter moves through; they sway in wind and hide the hunter when crouched. | Hunt | Parallax layer | 3840×400 | 3 strips | Scroll at 1.0–1.3×. Edges clean for the sway shader. | res://art/hunt/hnt_03_stalk_scene_near_grass_strips.png | Production | Must | F12 | No | 6 | Not started
HNT-04 | Hunting (stalk and loose) | Caribou | Caribou (the deer the sagas mention): graze, head up, ear flick when alert, startle, flee, and a fall when hit that shows no wound. | Hunt | Sprite sheet | 420×320 per frame | graze 8, alert 4, ear flick 3, flee 8, fall 6 | Side view, centre-bottom pivot. Ear flick is the visual twin of the alert heartbeat. | res://art/hunt/hnt_04_caribou_strip.png | Production | Must | F12 | No | 14 | Not started
HNT-05 | Hunting (stalk and loose) | Ground birds and waterfowl | Eider ducks and ptarmigan: idle, walk, take-off flock, and a fall frame. | Hunt, Forage | Sprite sheet | 160×120 per frame | idle 4, walk 6, take-off 8, fall 3 | Centre-bottom pivot. | res://art/hunt/hnt_05_ground_birds_and_waterfowl_strip.png | Production | Should | F12 | No | 6 | Not started
HNT-06 | Hunting (stalk and loose) | Hunter character (side view) | The crew hunter in a hooded wool tunic with a short bow and quiver: walk, crouch-walk, draw and hold, loose, lower bow, startle. | Hunt | Cutout rig parts + animations | 360×420 bounding | walk, crouch-walk, draw, hold, loose, lower | Godot Skeleton2D cutout: deliver separate parts (head, torso, upper and lower arms, hands, legs, bow, quiver) on one canvas with pivots marked. Hunt scale (about 340 px tall). | res://art/hunt/hnt_06_hunter_character/ (one PNG per part) | Production | Must | F12 | No | 14 | Not started
HNT-07 | Hunting (stalk and loose) | Arrow and bowstring | Arrow in flight, an arrow stuck in the ground, and a bowstring tension highlight for full draw. | Hunt | Sprite set | 160×24 arrow | 3 sprites | Arrow pivot at the nock. | res://art/hunt/hnt_07_arrow_and_bowstring.png | Production | Must | F12 | No | 1 | Not started
HNT-08 | Hunting (stalk and loose) | Wound and miss marks | Non-gory feedback: a puff of fur and dust on a hit, a clod of turf on a miss. | Hunt | Sprite sheet | 128×128 per frame | hit 5, miss 5 | No blood. Tone guide: "no gore gallery". | res://art/hunt/hnt_08_wound_and_miss_marks_strip.png | Production | Must | F12 | No | 1 | Not started
FOR-01 | Foraging (patch reading) | Berry patch (top-down) | Close top-down view of low heath with blueberry and partridgeberry clumps among moss, lichen, and stones. | Forage | Background plate | 1920×1200 (1080 safe) | 3 states (healthy, thinned, stripped) | Same framing in all states so they cross-fade. | res://art/forage/for_01_berry_patch.png | Production | Must | F13 | Yes | 8 | Not started
FOR-02 | Foraging (patch reading) | Wild grain patch (top-down) | Self-sown wild grain (lyme grass) heads among coastal grass, with bare sand between clumps. | Forage | Background plate | 1920×1200 (1080 safe) | 3 states | As above. | res://art/forage/for_02_wild_grain_patch.png | Production | Must | F13 | Yes | 7 | Not started
FOR-03 | Foraging (patch reading) | Shore patch: mussels and kelp | Low-tide rocks with mussel beds, kelp, and tide pools from above. | Forage | Background plate | 1920×1200 (1080 safe) | 3 states | As above. | res://art/forage/for_03_shore_patch_mussels_and_kelp.png | Production | Should | F13 | Yes | 7 | Not started
FOR-04 | Foraging (patch reading) | Bird cliff egg ledges | Ledges of a bird island crowded with nests and eggs; birds rise when the forager is greedy or loud. | Forage | Background plate | 1920×1200 (1080 safe) | 2 states | Pairs with the seabird flock sheet for the noise meter. | res://art/forage/for_04_bird_cliff_egg_ledges.png | Production | Could | F13 | Yes | 6 | Not started
FOR-05 | Foraging (patch reading) | Vine and grape clusters (Hóp) | Wild grape vines with small dark clusters, the find that names Vinland, for the Hóp forage patch. | Forage | Sprite set | 256×256 | 4 variants | Overlay on a patch; only at Hóp. | res://art/forage/for_05_vine_and_grape_clusters.png | Alpha | Should | F27 | No | 3 | Not started
FOR-06 | Foraging (patch reading) | Forage pickups | Individual items the hand picks: berries, grain heads, mussels, eggs, angelica stems, and roots. | Forage | Sprite set | 96×96 each | 6 items × 2 sizes | Centre pivot. | res://art/forage/for_06_forage_pickups.png | Production | Must | F13 | No | 3 | Not started
FOR-07 | Foraging (patch reading) | Reaching hand | A hand seen from above reaching, closing on an item, and pulling back. | Forage | Sprite sheet | 256×256 per frame | reach 4, grab 3 | Pivot at the wrist. | res://art/forage/for_07_reaching_hand_strip.png | Production | Must | F13 | No | 3 | Not started
FOR-08 | Foraging (patch reading) | Basket (top-down) | Woven basket seen from above, in five fill states from empty to heaped; the visual twin of the take tick. | Forage | Sprite set | 360×360 | 5 states | Centre pivot; bottom-right of the screen. | res://art/forage/for_08_basket.png | Production | Must | F13 | No | 3 | Not started
BLD-01 | Building (joint, lift, smoke rack) | Joint workbench close-up | Close-up of a trestle with a squared timber, a drilled hole, and wood shavings, seen at a low three-quarter angle. | Joint | Background plate | 1920×1200 (1080 safe) | 2 variants (dry, rain-darkened) | Static; the log and peg are separate. | res://art/build/bld_01_joint_workbench_close_up.png | Vertical slice | Must | F07 | Yes | 6 | Not started
BLD-02 | Building (joint, lift, smoke rack) | Timber pieces with grain | The working timber in three woods (spruce, birch, larch driftwood), each with visible grain lines and a mortise hole. | Joint | Sprite set | 1400×400 | 3 woods | The grain lines are a separate layer so code can tint them red when the drive is cross-grain (visual twin). | res://art/build/bld_02_timber_pieces_with_grain.png | Vertical slice | Must | F07 | No | 6 | Not started
BLD-03 | Building (joint, lift, smoke rack) | Treenail peg | A wooden peg in three states: loose, half driven, fully seated flush. | Joint | Sprite set | 120×360 | 3 states | Pivot at the peg tip. | res://art/build/bld_03_treenail_peg.png | Vertical slice | Must | F07 | No | 1 | Not started
BLD-04 | Building (joint, lift, smoke rack) | Mallet and hands | A wooden mallet in a gripping hand with the other hand bracing, in raised and struck positions. | Joint | Sprite set | 700×600 | raise 3, strike 3 | Pivot at the wrist. | res://art/build/bld_04_mallet_and_hands.png | Vertical slice | Must | F07 | No | 4 | Not started
BLD-05 | Building (joint, lift, smoke rack) | Split log state | The timber cracked along the grain with a long split; a failure state. | Joint | Sprite set | 1400×400 | 1 per wood | Swaps in for the timber piece. | res://art/build/bld_05_split_log_state.png | Vertical slice | Must | F07 | No | 2 | Not started
BLD-06 | Building (joint, lift, smoke rack) | Wood chips and dust | Small chips and a dust puff on each mallet strike. | Joint, Lift | Sprite sheet | 128×128 per frame | 6 frames | Centre pivot. | res://art/build/bld_06_wood_chips_and_dust_strip.png | Vertical slice | Must | F07 | No | 1 | Not started
BLD-07 | Building (joint, lift, smoke rack) | Lift scene: frame and hauling crew | Side view of shear legs with a rope and block lifting a heavy timber into place against a half-built wall, four crew hauling on the rope. | Lift | Background plate + rig | 1920×1080 | background + 4 hauler poses (lean, heave, slip, rest) | Haulers as cutout parts or 4-pose sheets; rope drawn in code. | res://art/build/bld_07_lift_scene_frame_and_hauling_crew.png | Production | Must | F18 | Yes | 12 | Not started
BLD-08 | Building (joint, lift, smoke rack) | Lifted timbers | A wall beam, a ridge beam, and the mast being raised, each swinging on the rope. | Lift | Sprite set | 1200×200 beams, 200×1000 mast | 3 pieces | Pivot at the rope point. | res://art/build/bld_08_lifted_timbers.png | Production | Must | F18 | No | 3 | Not started
BLD-09 | Building (joint, lift, smoke rack) | Slipway surf and log rollers | Log rollers on the shingle with surf washing up between them, for lifting at the slipway. | Lift | Foreground layer | 1920×400 | 8-frame surf loop | Bottom-anchored. | res://art/build/bld_09_slipway_surf_and_log_rollers.png | Production | Must | F18 | No | 4 | Not started
BLD-10 | Building (joint, lift, smoke rack) | Cracked timber state | A beam with a long crack and splinters, for a failed lift. | Lift | Sprite set | 1200×200 | 1 | Swaps in for a lifted beam. | res://art/build/bld_10_cracked_timber_state.png | Production | Must | F18 | No | 1 | Not started
BLD-11 | Building (joint, lift, smoke rack) | Smoke rack close-up | A wooden drying rack of split fish over a low fire pit, seen close and slightly from below. | Smoke rack | Background plate | 1920×1200 (1080 safe) | 1 | Fire and smoke are separate. | res://art/build/bld_11_smoke_rack_close_up.png | Production | Must | F15 | Yes | 6 | Not started
BLD-12 | Building (joint, lift, smoke rack) | Fire pit flames | Fire at three heats: low smoulder, good steady fire, too hot with leaping flames. | Smoke rack, Camp | Sprite sheet | 256×320 per frame | 8 frames × 3 heats | Bottom pivot. Loops. | res://art/build/bld_12_fire_pit_flames_strip.png | Production | Must | F15 | No | 5 | Not started
BLD-13 | Building (joint, lift, smoke rack) | Smoke column | A rising smoke column whose colour shifts from thin white (good) to grey to black (too hot); it bends when the wind shoves it. | Smoke rack, Camp | Sprite sheet | 256×768 per frame | 8 frames × 3 colours | Bottom pivot. The colour shift is the visual twin of the haptic warmth ramp. | res://art/build/bld_13_smoke_column_strip.png | Production | Must | F15 | No | 4 | Not started
BLD-14 | Building (joint, lift, smoke rack) | Fish on the rack | Split fish in four states: fresh and wet, drying, fully dried (stockfish), and spoiled. | Smoke rack, Camp | Sprite set | 160×320 | 4 states | Top pivot (they hang). | res://art/build/bld_14_fish_on_the_rack.png | Production | Must | F15 | No | 3 | Not started
BAL-01 | Storm bail | Hull interior in a storm | Inside the open hold looking aft: ribs and strakes, lashed cargo under hides, crew braced, grey storm light from above, water sloshing in the bilge. | Storm bail | Background plate | 1920×1200 (1080 safe) | 1 | Static; water level is a separate layer. | res://art/storm_bail/bal_01_hull_interior_in_a_storm.png | Production | Must | F10 | Yes | 8 | Not started
BAL-02 | Storm bail | Bilge water level | Sloshing water surface strip that rises and falls inside the hold. | Storm bail | Tileable layer | 3840×300 | 8-frame loop | Code sets its height from the water amount. | res://art/storm_bail/bal_02_bilge_water_level.png | Production | Must | F10 | No | 4 | Not started
BAL-03 | Storm bail | Bailer and bailing crew | A wooden bailing scoop in two hands, with scoop, lift, and throw poses; two background crew bailing in rhythm. | Storm bail | Sprite sheet | 600×600 per frame | scoop 3, lift 3, throw 3 | The rhythm is the visual twin of the wave-set rumble. | res://art/storm_bail/bal_03_bailer_and_bailing_crew_strip.png | Production | Must | F10 | No | 6 | Not started
BAL-04 | Storm bail | Wave over the side (interior) | A wave crashing over the gunwale into the hold, seen from inside. | Storm bail | Sprite sheet | 1920×700 per frame | 10 frames | Top-anchored. | res://art/storm_bail/bal_04_wave_over_the_side_strip.png | Production | Must | F10 | No | 5 | Not started
BAL-05 | Storm bail | Leak jet and lost cask | Water jetting through a sprung strake, and a cask breaking loose and going over the side. | Storm bail | Sprite sheet | 400×300 per frame | jet 6, cask 8 | Centre pivot. | res://art/storm_bail/bal_05_leak_jet_and_lost_cask_strip.png | Production | Must | F45 | No | 3 | Not started
BAL-06 | Storm bail | Bailing metronome and water line | The no-haptic twin: a small carved bucket icon that swings in time, and a painted water-line mark on a rib. | Storm bail | UI sprite | 128×128 | 2 sprites | Shown when haptics are off. | res://art/storm_bail/bal_06_bailing_metronome_and_water_line.png | Production | Must | F32 | No | 1 | Not started
CMP-01 | Camp: ground, seasons and buildings | Camp ground: summer | The colony site seen side-on as a wide diorama: grassy terrace, the brook, the bog edge, the shingle shore on the right with the sea beyond. Empty build plots marked by flat ground. | Camp, Market | Background plate | 3840×1080 | 1 | Camera pans across it. Build plots at fixed x positions (see Scenes). Horizon at y = 540. | res://art/camp/cmp_01_camp_ground_summer.png | Vertical slice | Must | F06 | Yes | 14 | Not started
CMP-02 | Camp: ground, seasons and buildings | Camp ground: late summer (hay) | The same view with tall golden grass ready to cut and hay drying in rows. | Camp | Background plate | 3840×1080 | 1 | Same framing as summer. | res://art/camp/cmp_02_camp_ground_late_summer.png | Production | Must | F16 | Yes | 8 | Not started
CMP-03 | Camp: ground, seasons and buildings | Camp ground: autumn | Browning grass, wet ground, heavier sea, fewer leaves on the birches. | Camp | Background plate | 3840×1080 | 1 | Same framing. | res://art/camp/cmp_03_camp_ground_autumn.png | Production | Must | F47 | Yes | 8 | Not started
CMP-04 | Camp: ground, seasons and buildings | Camp ground: winter | Snow cover with drifts against everything, frozen brook, ice along the shore. | Camp | Background plate | 3840×1080 | 1 | Same framing. | res://art/camp/cmp_04_camp_ground_winter.png | Production | Must | F47 | Yes | 8 | Not started
CMP-05 | Camp: ground, seasons and buildings | Camp ground: spring thaw | Patchy snow, mud, brown grass greening at the edges, meltwater running. | Camp | Background plate | 3840×1080 | 1 | Same framing. | res://art/camp/cmp_05_camp_ground_spring_thaw.png | Production | Should | F47 | Yes | 8 | Not started
CMP-06 | Camp: ground, seasons and buildings | Camp far hills layer | Low hills and forest edge behind the camp, in summer and winter versions. | Camp | Parallax layer | 3840×500 | 2 seasons | Scrolls at 0.6×. | res://art/camp/cmp_06_camp_far_hills_layer.png | Vertical slice | Must | F06 | Yes | 6 | Not started
CMP-07 | Camp: ground, seasons and buildings | Booth (búð) | Temporary turf-and-timber booth with a hide or sail-cloth roof: plot marked, frame up, finished, and storm-damaged. | Camp | Building sprite | 420×300 | 4 stages | Bottom-centre pivot on the plot line. | res://art/camp/cmp_07_booth.png | Vertical slice | Must | F17 | No | 6 | Not started
CMP-08 | Camp: ground, seasons and buildings | Longhouse | The hall: thick turf walls on a timber frame, a turf roof, a smoke hole, a single door. Plot marked, timber frame, walls rising, complete, snowed in. | Camp | Building sprite | 1100×420 | 5 stages | Bottom-centre pivot. The frame stage must match the lift scene. | res://art/camp/cmp_08_longhouse.png | Production | Must | F17 | No | 14 | Not started
CMP-09 | Camp: ground, seasons and buildings | Byre | Cow shed with turf walls, stall partitions visible through the door, a hay loft: plot, frame, complete, snowed in. | Camp | Building sprite | 700×360 | 4 stages | Bottom-centre pivot. | res://art/camp/cmp_09_byre.png | Production | Must | F17 | No | 9 | Not started
CMP-10 | Camp: ground, seasons and buildings | Boat shed and slipway | Long open-ended boat shed (naust) above the shingle, with the slipway running down to the water: plot, frame, complete. | Camp | Building sprite | 1500×450 | 3 stages | Right end of the camp, at the shore. | res://art/camp/cmp_10_boat_shed_and_slipway.png | Production | Must | F18 | No | 10 | Not started
CMP-11 | Camp: ground, seasons and buildings | Palisade | Sharpened-stake palisade segments, straight and corner, plus a gate. Building it raises fear. | Camp | Building sprite | 300×260 per segment | 3 pieces × 2 stages | Tileable along the camp edge. | res://art/camp/cmp_11_palisade.png | Production | Must | F19 | No | 5 | Not started
CMP-12 | Camp: ground, seasons and buildings | Smoke rack (camp scale) | The drying rack at camp scale, empty, half-loaded, and full. | Camp | Building sprite | 360×300 | 3 states | Fire uses the fire pit sheet scaled down. | res://art/camp/cmp_12_smoke_rack.png | Production | Must | F15 | No | 3 | Not started
CMP-13 | Camp: ground, seasons and buildings | Smithy hut | A small turf hut with a forge for bog iron (the site had one), with a glow at the door when working. | Camp | Building sprite | 420×300 | 3 stages | Optional building. | res://art/camp/cmp_13_smithy_hut.png | Production | Could | F17 | No | 5 | Not started
CMP-14 | Camp: ground, seasons and buildings | Haystacks | Hay drying racks and stacks in four sizes, from a few rows to a winter's supply. Shows how much hay there is at a glance. | Camp | Sprite set | 300×260 | 4 sizes | Bottom pivot. | res://art/camp/cmp_14_haystacks.png | Production | Must | F16 | No | 3 | Not started
CMP-15 | Camp: ground, seasons and buildings | Timber stack | Seasoned timber stacked for the return cargo; seven states from 0 to 6+ units so the player can count it. | Camp | Sprite set | 500×240 | 7 states | Bottom pivot by the boat shed. | res://art/camp/cmp_15_timber_stack.png | Alpha | Must | F25 | No | 4 | Not started
CMP-16 | Camp: ground, seasons and buildings | Camp props | Cooking fire with a soapstone pot, firewood pile, warp-weighted loom, casks and chests, tool rack, drying hides on a frame, a sledge. | Camp | Sprite set | up to 300×300 | 10 props | Bottom pivot. | res://art/camp/cmp_16_camp_props.png | Vertical slice | Must | F06 | No | 10 | Not started
CMP-17 | Camp: ground, seasons and buildings | Cairn | A small stone cairn with a wooden marker; added for each death. Quiet and respectful. | Camp | Sprite | 160×140 | 2 variants | Bottom pivot. | res://art/camp/cmp_17_cairn.png | Production | Must | F46 | No | 1 | Not started
CMP-18 | Camp: ground, seasons and buildings | Snow drift and frost overlays | Snow caps for each building's roof and drifts against walls; frost rime for winter mornings. | Camp | Overlay | matches each building | 1 per building | Aligned to each complete building. | res://art/camp/cmp_18_snow_drift_and_frost_overlays.png | Production | Must | F47 | No | 4 | Not started
CMP-19 | Camp: ground, seasons and buildings | Job markers | Small carved wooden pegs marking where today's jobs are on the camp ground, with a highlighted state. | Camp | UI sprite | 96×128 | 2 states | Bottom pivot. | res://art/camp/cmp_19_job_markers.png | Vertical slice | Must | F06 | No | 1 | Not started
ANI-01 | Livestock | Bull | A powerful dark Norse bull with short horns: idle, walk, graze, agitated (head down, pawing), and charging. The bull is a trade risk; when loose he must look dangerous. | Camp, Market, Voyage | Sprite sheet | 420×300 per frame | idle 4, walk 8, graze 6, agitated 6, charge 8 | Side view, bottom-centre pivot. Camp scale. | res://art/animals/ani_01_bull_strip.png | Production | Must | F21 | No | 12 | Not started
ANI-02 | Livestock | Cow | Small hardy cow, light dun or red: idle, walk, graze, being milked, lying down; plus a thin winter variant. | Camp, Voyage | Sprite sheet | 360×260 per frame | idle 4, walk 8, graze 6, milked 4, lie 3 | As above. Thin variant as a separate palette swap or sheet. | res://art/animals/ani_02_cow_strip.png | Production | Must | F16 | No | 12 | Not started
ANI-03 | Livestock | Calf | A calf that follows a cow: idle and walk. | Camp | Sprite sheet | 220×180 per frame | idle 4, walk 8 | As above. | res://art/animals/ani_03_calf_strip.png | Production | Could | F16 | No | 4 | Not started
ANI-04 | Livestock | Sheep | Short-tailed Norse sheep with mixed fleece colours: idle, walk, graze, huddle (winter). | Camp, Voyage | Sprite sheet | 200×160 per frame | idle 4, walk 8, graze 6, huddle 3 | As above. Three fleece colour variants. | res://art/animals/ani_04_sheep_strip.png | Production | Must | F16 | No | 8 | Not started
ANI-05 | Livestock | Goat | A goat: idle, walk, climb onto a rock. | Camp | Sprite sheet | 200×180 per frame | idle 4, walk 8, climb 4 | As above. | res://art/animals/ani_05_goat_strip.png | Production | Could | F16 | No | 5 | Not started
CHR-01 | Crew and named characters | Crew body rigs | Base bodies for the crew at camp scale: man and woman in three builds each, delivered as cutout parts (head, torso, upper arms, forearms, hands, thighs, shins, feet) with pivots marked. | Camp, Market, Lift | Cutout rig parts | 200×360 bounding | 6 bodies | Godot Skeleton2D. Parts on one canvas per body, joints overlapping so rotation never shows a gap. | res://art/characters/chr_01_crew_body_rigs/ (one PNG per part) | Vertical slice | Must | F06 | No | 18 | Not started
CHR-02 | Crew and named characters | Crew clothing and hair sets | Swappable clothing for the rigs: wool tunics and dresses in natural, madder, woad blue, and lichen yellow, cloaks with pins, hoods, aprons with oval brooches, winter wraps; six hair styles and three beards. | Camp, Market | Cutout rig parts | per part | 12 outfits, 9 hair | Same part layout as the body rigs. | res://art/characters/chr_02_crew_clothing_and_hair_sets/ (one PNG per part) | Production | Must | F23 | No | 20 | Not started
CHR-03 | Crew and named characters | Crew animations | Cutout animations: idle, walk, carry a load, chop or hammer, haul, kneel to work, row (seated), bail, sit and rest, sick (lying, shivering), celebrate, grieve. | Camp, Voyage, Lift | Animation set | n/a | 12 animations | Built in Godot from the rigs. Deliver reference poses (key poses as PNGs) if Claude animates them. | res://art/characters/chr_03_crew_animations.png | Production | Must | F23 | No | 16 | Not started
CHR-04 | Crew and named characters | Role props | Props that mark the named crew roles: steering oar handle, smith's hammer and tongs, herder's crook and milk pail, bow and quiver, shipwright's broad axe, cook's ladle, healer's herb pouch, lookout's horn. | Camp, Voyage | Sprite set | up to 200×200 | 8 props | Pivot at the grip point. | res://art/characters/chr_04_role_props.png | Production | Must | F23 | No | 4 | Not started
CHR-05 | Crew and named characters | Crew role portraits | Head-and-shoulders portraits for the eight named roles, painted in the same style as the camp, each in neutral, worried, glad, and sick expressions. | UI: crew roster, events | Portrait | 256×256 | 8 roles × 4 expressions | Framed by the UI portrait frame. | res://art/characters/chr_05_crew_role_portraits.png | Production | Must | F23 | No | 24 | Not started
CHR-06 | Crew and named characters | Outfit leader portraits | Larger bust portraits for the four outfit leaders: the farm household's matriarch, the merchant (Karlsefni, with Gudrid as his partner), the hunter-boat skipper, and the shipwright's kin head. Neutral, glad, and grim each. | Loadout, events, endings | Portrait | 512×512 | 5 people × 3 expressions | Gudrid and Karlsefni are historical figures; keep them grounded and plain, not heroic. | res://art/characters/chr_06_outfit_leader_portraits.png | Production | Should | F22 | No | 20 | Not started
CHR-07 | Crew and named characters | Thorhall the Hunter portrait | The surly, half-pagan hunter of the saga who leaves to find Vinland his own way; neutral and grim. | Events | Portrait | 256×256 | 2 expressions | Only if the Thorhall split ships. | res://art/characters/chr_07_thorhall_the_hunter_portrait.png | Alpha | Could | F28 | No | 3 | Not started
CHR-08 | Crew and named characters | Newborn bundle | A swaddled infant in a wool wrap, held, and in a cradle; for the birth event (Snorri in the saga). | Camp, events | Sprite set | 160×160 | 2 states | Bottom pivot. | res://art/characters/chr_08_newborn_bundle.png | Production | Should | F48 | No | 2 | Not started
MKT-01 | Market and visitors (consultant review) | Visitors' skin boats | The visitors arrive in skin boats (húðkeipar, as the sagas call them) pulled up on the shore near the camp. Shape, covering, and paddles must follow the consultant's guidance; start as rough silhouettes only. | Market, Camp | Sprite set | 700×200 | 3 boats | Draft only until the cultural review (F59) signs off. | res://art/market/mkt_01_visitors_skin_boats.png | Production | Must | F59 | No | 6 | Not started
MKT-02 | Market and visitors (consultant review) | Visitor characters | Six individual visitors, each with their own reason for being at the market (a trader, an elder, a curious young person, a hunter, a woman bringing furs, a cautious watcher). Each is a person with dignity and their own goals; none is a generic "native". Animations: idle, walk, offer goods, examine an item, wary step back, leave quickly. | Market | Cutout rig parts + animations | 200×360 bounding | 6 people × 6 animations | Clothing, hair, and objects must follow the consultant's guidance (F59, Risk R11). Same rig layout as the crew. | res://art/market/mkt_02_visitor_characters/ (one PNG per part) | Production | Must | F20 | No | 40 | Not started
MKT-03 | Market and visitors (consultant review) | Visitor portraits | Portraits for the six visitors for trade dialogue, neutral and wary expressions. | Market UI | Portrait | 256×256 | 6 × 2 expressions | After consultant review. | res://art/market/mkt_03_visitor_portraits.png | Production | Must | F20 | No | 18 | Not started
MKT-04 | Market and visitors (consultant review) | Trade blanket and goods | A spread hide or cloth where goods are laid out: bolts of red cloth (full, half, a strip), milk in pails and skins, cheese rounds, and the visitors' furs and pelts. Iron blades shown only when the weapon-sale event is live. | Market | Sprite set | 1200×400 blanket, 128×128 goods | 1 blanket + 12 goods | Goods snap to slots on the blanket. | res://art/market/mkt_04_trade_blanket_and_goods.png | Production | Must | F20 | No | 8 | Not started
MKT-05 | Market and visitors (consultant review) | Market scene dressing | Extra shoreline dressing for market days: footprints in the shingle, a second cook fire, staked hides, children's toys left behind. | Market | Sprite set | up to 300×200 | 6 props | Bottom pivot. | res://art/market/mkt_05_market_scene_dressing.png | Production | Should | F20 | No | 3 | Not started
MAP-01 | Leg map | Leg map board | The route shown as a carved and painted wooden board (no parchment): the coast chain from Greenland through Helluland, Markland, and the Wonder Strands to the Strait and Hóp, stylised and saga-like, not a real chart. | Leg map | Background plate | 1920×1200 (1080 safe) | 2 variants (outbound summer, return autumn) | Node positions are listed on the Scenes sheet. | res://art/map/map_01_leg_map_board.png | Vertical slice | Must | F11 | No | 12 | Not started
MAP-02 | Leg map | Region emblems | A small carved emblem for each region: fjord farm (Eriksfjord), open water wave (Labrador Sea), flat stone (Helluland), spruce (Markland), long beach (Furðustrandir), booths (the Strait), vine (Hóp). | Leg map | Icon set | 160×160 | 7 emblems × 3 states (locked, available, visited) | Centre pivot. | res://art/map/map_02_region_emblems.png | Vertical slice | Must | F11 | No | 7 | Not started
MAP-03 | Leg map | Route segments | Painted route lines between nodes in three states: sailed, current, and not yet open; plus a dashed autumn return route. | Leg map | Sprite set | 512×64 tileable | 4 styles | Stretched along a path in code. | res://art/map/map_03_route_segments.png | Vertical slice | Must | F11 | No | 2 | Not started
MAP-04 | Leg map | Weather glyphs for the map | Seven small carved symbols matching the weather deck cards, shown on the map leg ahead. | Leg map, Voyage HUD | Icon set | 96×96 | 7 icons | Centre pivot. Same symbols as the card corners. | res://art/map/map_04_weather_glyphs_for_the_map.png | Production | Must | F09 | No | 3 | Not started
LOD-01 | Eriksfjord loadout | Eriksfjord quay | The departure scene: the knarr tied up at a stone and timber landing below Brattahlíð, people and animals waiting on the shore, goods piled. | Loadout | Background plate | 1920×1200 (1080 safe) | 1 | Upper half of the screen; the hold grid sits below. | res://art/loadout/lod_01_eriksfjord_quay.png | Production | Must | F53 | Yes | 10 | Not started
LOD-02 | Eriksfjord loadout | Hold cross-section grid | The knarr's hold seen from above as a carved board with 24 slots, ribs dividing it; bow at the right. | Loadout, HUD | UI sprite | 1600×480 | 1 + slot highlight | Slot positions exported as a JSON or listed in Scenes. | res://art/loadout/lod_02_hold_cross_section_grid.png | Vertical slice | Must | F53 | No | 5 | Not started
LOD-03 | Eriksfjord loadout | Cargo tokens | Tokens that fill hold slots: person, cattle (takes more than one slot), sheep, food unit, drink cask, fodder, trade goods, timber, and an empty-slot mark. Same symbols as the HUD icons, bigger. | Loadout, HUD | Icon set | 96×96 (cattle 144×96) | 9 tokens × 2 states | Centre pivot. | res://art/loadout/lod_03_cargo_tokens.png | Vertical slice | Must | F01 | No | 5 | Not started
LOD-04 | Eriksfjord loadout | Outfit cards | Four illustrated cards for the starting outfits: farm household (animals and fodder), merchant (red cloth and iron, a second hull), hunter-boat (boats, nets, bows), shipwright's kin (tools, spare sail, timber). | Loadout | Illustration | 600×800 | 4 cards | Card frame is a UI 9-slice; paint the illustration window only. | res://art/loadout/lod_04_outfit_cards.png | Production | Should | F22 | No | 20 | Not started
UIK-01 | UI kit (wood and wool) | Primary panel 9-slice | The main panel: a board of weathered pale timber with a carved border and a wool-felt inset for text. | All UI | 9-slice | 256×256 (margins 48) | 1 | Godot NinePatchRect. Margins on the Art Spec sheet. | res://art/ui/kit/uik_01_primary_panel_9_slice.png | Vertical slice | Must | F36 | No | 3 | Not started
UIK-02 | UI kit (wood and wool) | Secondary panel and tooltip 9-slices | A thinner plank panel for small boxes and a wool-tag tooltip with a stitched edge. | All UI | 9-slice | 128×128 (margins 24) | 2 | As above. | res://art/ui/kit/uik_02_secondary_panel_and_tooltip_9_slices.png | Vertical slice | Must | F36 | No | 3 | Not started
UIK-03 | UI kit (wood and wool) | Buttons | Wooden buttons with a carved face in four states: normal, focused (gamepad), pressed, disabled. The focused state must be obvious from across a room. | All UI | 9-slice | 192×64 (margins 24) | 4 states | Focus state doubles as the hover state for mouse. | res://art/ui/kit/uik_03_buttons.png | Vertical slice | Must | F36 | No | 3 | Not started
UIK-04 | UI kit (wood and wool) | Tabs, toggles, sliders, checkboxes | Remaining controls in the same material: tabs (on and off), a toggle switch, a slider track with a wooden knob, a checkbox with a stitched X. | Menus, Options | Sprite set | various | 10 sprites | For the options menu (F51). | res://art/ui/kit/uik_04_tabs_toggles_sliders_checkboxes.png | Production | Must | F51 | No | 4 | Not started
UIK-05 | UI kit (wood and wool) | Meter frames and fills | A carved meter frame with yarn-wound fills in five colours (food, drink, fodder, hull, morale). | HUD | 9-slice + fills | 256×48 | 1 frame + 5 fills | Fill is a separate 9-slice so it scales cleanly. | res://art/ui/kit/uik_05_meter_frames_and_fills.png | Vertical slice | Must | F36 | No | 2 | Not started
UIK-06 | UI kit (wood and wool) | Scroll bar and divider | A scroll bar (track and grip) and a carved divider line. | Menus | Sprite set | 24×256, 512×16 | 3 sprites | Simple. | res://art/ui/kit/uik_06_scroll_bar_and_divider.png | Production | Must | F51 | No | 1 | Not started
UIK-07 | UI kit (wood and wool) | Dialogue and choice panel | A wide bottom panel for event text and two to four choice buttons, with a portrait window on the left. | Events, Market | 9-slice | 512×256 (margins 64) | 1 + portrait frame | Portrait frame fits 256×256 portraits. | res://art/ui/kit/uik_07_dialogue_and_choice_panel.png | Vertical slice | Must | F06 | No | 3 | Not started
UIK-08 | UI kit (wood and wool) | Toast and notification tag | A small wool tag that slides in for short messages (fix result, autosave, item gained). | All UI | 9-slice | 256×64 | 1 | Top-centre. | res://art/ui/kit/uik_08_toast_and_notification_tag.png | Vertical slice | Must | F36 | No | 1 | Not started
UIK-09 | UI kit (wood and wool) | Event card frame | Card frame for weather and event cards: a carved wooden border with a corner slot for the weather glyph, an 800×450 illustration window, and a text area. | Events | UI frame | 880×760 | 1 | Illustration window at 40,40. | res://art/ui/kit/uik_09_event_card_frame.png | Vertical slice | Must | F09 | No | 3 | Not started
HUD-01 | HUD instruments | Hold tally stick | The hold shown as a carved tally stick with 24 notches; filled notches are inked, the cargo type is shown by a small symbol under each group. Changes animate one notch at a time. | Voyage, Camp HUD | UI sprite | 1200×120 | stick + notch states (empty, filled, over) | The game's most important HUD element. Notch positions on the Scenes sheet. | res://art/ui/hud/hud_01_hold_tally_stick.png | Vertical slice | Must | F36 | No | 5 | Not started
HUD-02 | HUD instruments | Ration selector | Three carved bowl icons: full, half, bare bones; with a separate small trough for the animals' ration. | Voyage, Camp HUD | Icon set | 96×96 | 4 icons × 2 states | Selected state is brighter with a wool tag. | res://art/ui/hud/hud_02_ration_selector.png | Vertical slice | Must | F01 | No | 2 | Not started
HUD-03 | HUD instruments | Pace selector | Three sail-and-wave icons: crack on (full sail, spray), easy (reefed), heave to (furled, bow into the wind). | Voyage HUD | Icon set | 96×96 | 3 icons × 2 states | As above. | res://art/ui/hud/hud_03_pace_selector.png | Vertical slice | Must | F38 | No | 2 | Not started
HUD-04 | HUD instruments | Season dial | A carved wooden wheel divided into months from May to October plus a dark winter segment, with a pointer and a red danger arc on October at sea. | Voyage, Camp HUD | UI sprite | 320×320 | wheel + pointer + danger arc | Pointer rotates in code. | res://art/ui/hud/hud_04_season_dial.png | Vertical slice | Must | F35 | No | 3 | Not started
HUD-05 | HUD instruments | Watch and day counter | Six notches for the six four-hour watches of a day, a sun and moon marker, and a day-number plate. | Voyage HUD | UI sprite | 320×80 | base + 6 notch states | Top-left HUD. | res://art/ui/hud/hud_05_watch_and_day_counter.png | Vertical slice | Must | F02 | No | 2 | Not started
HUD-06 | HUD instruments | Goodwill and fear cord | A wool cord with five knots for fear and beads for goodwill; knots tighten and darken as fear rises to the cap. | Camp, Market HUD | UI sprite | 480×96 | cord + 5 knot states + bead states | Fear cap matches Assumptions (5). | res://art/ui/hud/hud_06_goodwill_and_fear_cord.png | Production | Must | F19 | No | 3 | Not started
HUD-07 | HUD instruments | Ship condition icons | Hull icon in four states (sound, strained, sprung, holed) and sail icon in three (whole, torn, lost). | Voyage HUD | Icon set | 96×96 | 7 icons | Bottom-left HUD. | res://art/ui/hud/hud_07_ship_condition_icons.png | Production | Must | F45 | No | 2 | Not started
HUD-08 | HUD instruments | Morale and sickness icons | Small faces or hearth icons for crew morale (high, steady, low, broken) and a sickness mark. | Voyage, Camp HUD | Icon set | 64×64 | 5 icons | Used in the roster. | res://art/ui/hud/hud_08_morale_and_sickness_icons.png | Production | Must | F46 | No | 2 | Not started
HUD-09 | HUD instruments | Latitude readout and drift arrow | A carved notch scale showing estimated latitude, and a curved arrow for drift direction and size. | Voyage HUD | UI sprite | 96×320, 160×160 | 2 sprites | Arrow rotates and scales in code. | res://art/ui/hud/hud_09_latitude_readout_and_drift_arrow.png | Vertical slice | Must | F38 | No | 2 | Not started
HUD-10 | HUD instruments | Crew roster card | A small card per crew member: portrait window, role symbol, health and morale marks. | Camp, Voyage | UI frame | 320×120 | 1 + states | Uses role portraits. | res://art/ui/hud/hud_10_crew_roster_card.png | Production | Must | F23 | No | 2 | Not started
HUD-11 | HUD instruments | Haptics-off cue marks | The on-screen twins for vibration cues not covered elsewhere: a pulse ring, a tug mark, a tick mark, and a warning flash for strain. | All mini-games | Icon set | 128×128 | 4 icons | Shown only when haptics are off (F32). | res://art/ui/hud/hud_11_haptics_off_cue_marks.png | Beta | Must | F32 | No | 2 | Not started
ICN-01 | Resource and item icons | Resource icons | One clear icon per resource: food unit, drink cask, fodder, hay, timber, red cloth, iron, milk, cheese, hides, meat, fresh fish, dried fish, berries, grain, silver. Carved-and-painted look, readable at 48 px. | HUD, Loadout, Market | Icon set | 128×128 (shown at 48–96) | 16 icons | Centre pivot. Same style as the cargo tokens. | res://art/ui/icons/icn_01_resource_icons.png | Vertical slice | Must | F01 | No | 8 | Not started
ICN-02 | Resource and item icons | Verb icons | Five icons for the five verbs: navigate (star ring), fish (hook), hunt (bow), forage (basket), build (mallet). | Camp job board, menus | Icon set | 128×128 | 5 icons | Used on job markers and the Dashboard-style summary screen. | res://art/ui/icons/icn_02_verb_icons.png | Vertical slice | Must | F06 | No | 2 | Not started
ICN-03 | Resource and item icons | Status and event icons | Small icons for: sick, dead, birth, fear tick, goodwill gain, storm, spoiled, autosave. | HUD, toasts | Icon set | 64×64 | 8 icons | Autosave icon is a turning spindle whorl. | res://art/ui/icons/icn_03_status_and_event_icons.png | Production | Must | F50 | No | 3 | Not started
ICN-04 | Resource and item icons | Controller button glyphs | Button prompts for Xbox, PlayStation, and Steam Deck layouts (face buttons, bumpers, triggers, sticks with direction hints, d-pad, menu buttons) plus keyboard and mouse. | All UI | Icon set | 64×64 | about 90 glyphs | A free CC0 set (Kenney Input Prompts) is acceptable; restyle the frame to wood if time allows. | res://art/ui/icons/icn_04_controller_button_glyphs.png | Vertical slice | Must | F08 | Yes | 4 | Not started
ICN-05 | Resource and item icons | Mouse cursor | A small carved pointer and a grab hand, for the mouse fallback. | All UI | Cursor | 48×48 | 2 cursors | Hotspot at the tip. | res://art/ui/icons/icn_05_mouse_cursor.png | Alpha | Should | F54 | No | 1 | Not started
ICN-06 | Resource and item icons | Achievement icons | Twelve achievement badges tied to saga beats (first clean fix, first winter survived, a birth, timber home, relief ship, full win), each with a greyed locked version. | Steam | Icon set | 256×256 | 12 × 2 states | Steam requires both versions as JPG or PNG. | res://art/ui/icons/icn_06_achievement_icons.png | Beta | Should | F58 | No | 8 | Not started
EVT-01 | Event and weather card illustrations | Weather card: fog | The knarr ghosting through white fog, only the sail top visible. | Events | Illustration | 800×450 | 1 | Fits the event card window. | res://art/events/evt_01_weather_card_fog.png | Production | Must | F09 | No | 4 | Not started
EVT-02 | Event and weather card illustrations | Weather card: low cloud | Scud racing over a grey sea, a gull struggling in the wind. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_02_weather_card_low_cloud.png | Production | Must | F09 | No | 4 | Not started
EVT-03 | Event and weather card illustrations | Weather card: following gale | The ship running fast down long streaked seas under a reefed sail, spray flying. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_03_weather_card_following_gale.png | Production | Must | F09 | No | 4 | Not started
EVT-04 | Event and weather card illustrations | Weather card: beam sea | The ship heeled hard with green water slopping over the lee gunwale. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_04_weather_card_beam_sea.png | Production | Must | F09 | No | 4 | Not started
EVT-05 | Event and weather card illustrations | Weather card: storm | The knarr hove to under a black sky, crew bailing, a wave towering astern. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_05_weather_card_storm.png | Production | Must | F10 | No | 4 | Not started
EVT-06 | Event and weather card illustrations | Weather card: drift ice | Floes all around the hull, a crew member fending off with an oar. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_06_weather_card_drift_ice.png | Production | Must | F09 | No | 4 | Not started
EVT-07 | Event and weather card illustrations | Weather card: calm | Glassy water, sail hanging slack, crew at the oars. | Events | Illustration | 800×450 | 1 | As above. | res://art/events/evt_07_weather_card_calm.png | Production | Must | F09 | No | 4 | Not started
EVT-08 | Event and weather card illustrations | Event: landfall | The first sight of a new coast from the deck, the crew pointing. One per region is ideal; one shared image is the minimum. | Events | Illustration | 800×450 | 1 (up to 6) | Could reuse the near coast strips with a crew foreground. | res://art/events/evt_08_event_landfall.png | Production | Must | F11 | No | 5 | Not started
EVT-09 | Event and weather card illustrations | Event: sprung strake | A plank seam springing open, water jetting in, a crew member shoving a wad of wool into it. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_09_event_sprung_strake.png | Production | Must | F45 | No | 4 | Not started
EVT-10 | Event and weather card illustrations | Event: man overboard | A figure in the water reaching up, a rope thrown from the gunwale. | Events | Illustration | 800×450 | 1 | Not graphic. | res://art/events/evt_10_event_man_overboard.png | Production | Must | F10 | No | 4 | Not started
EVT-11 | Event and weather card illustrations | Event: cask breached | A split water cask gushing across the deck. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_11_event_cask_breached.png | Vertical slice | Must | F37 | No | 3 | Not started
EVT-12 | Event and weather card illustrations | Event: sickness | A crew member lying under a cloak in the hold, another giving them whey. | Events | Illustration | 800×450 | 1 | Quiet tone. | res://art/events/evt_12_event_sickness.png | Production | Must | F46 | No | 4 | Not started
EVT-13 | Event and weather card illustrations | Event: a death | Stones being set on a cairn at dusk, crew standing with heads bowed. | Events | Illustration | 800×450 | 1 | Respectful, no body shown. | res://art/events/evt_13_event_a_death.png | Production | Must | F46 | No | 4 | Not started
EVT-14 | Event and weather card illustrations | Event: a birth | Inside a booth by firelight, a mother holding a newborn, women around her. | Events | Illustration | 800×450 | 1 | Warm, tender. | res://art/events/evt_14_event_a_birth.png | Production | Should | F48 | No | 4 | Not started
EVT-15 | Event and weather card illustrations | Event: the bull breaks loose | The bull charging out of the byre toward the market blanket, visitors scattering. | Events | Illustration | 800×450 | 1 | The saga moment; drama without violence. | res://art/events/evt_15_event_the_bull_breaks_loose.png | Production | Must | F21 | No | 5 | Not started
EVT-16 | Event and weather card illustrations | Event: the weapon request | A visitor gesturing toward an iron blade on the trade blanket; a crew member hesitating. | Events | Illustration | 800×450 | 1 | After consultant review. | res://art/events/evt_16_event_the_weapon_request.png | Production | Must | F21 | No | 4 | Not started
EVT-17 | Event and weather card illustrations | Event: market day arrives | Skin boats landing on the shingle at morning, the camp coming out to meet them. | Events | Illustration | 800×450 | 1 | After consultant review. | res://art/events/evt_17_event_market_day_arrives.png | Production | Must | F20 | No | 5 | Not started
EVT-18 | Event and weather card illustrations | Event: hay harvest | Crew cutting tall grass with scythes in late-summer light. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_18_event_hay_harvest.png | Production | Must | F16 | No | 4 | Not started
EVT-19 | Event and weather card illustrations | Event: first snow | The first snow settling on the turf roofs, smoke rising, livestock huddled. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_19_event_first_snow.png | Production | Must | F47 | No | 4 | Not started
EVT-20 | Event and weather card illustrations | Event: relief ship sighted | A sail on the horizon, the camp running to the shore. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_20_event_relief_ship_sighted.png | Alpha | Must | F26 | No | 4 | Not started
EVT-21 | Event and weather card illustrations | Event: timber cargo departs | The knarr loaded with timber pushing off from the slipway, waving crew. | Events, trailer | Illustration | 800×450 | 1 | Also the trailer's closing image. | res://art/events/evt_21_event_timber_cargo_departs.png | Alpha | Must | F25 | No | 5 | Not started
EVT-22 | Event and weather card illustrations | Event: recruitment at Eriksfjord | Crew retelling the voyage to a crowd at Brattahlíð; young people stepping forward. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_22_event_recruitment_at_eriksfjord.png | Alpha | Must | F26 | No | 4 | Not started
EVT-23 | Event and weather card illustrations | Event: Thorhall leaves | A small party walking away along the shore, Thorhall in front. | Events | Illustration | 800×450 | 1 | Only if F28 ships. | res://art/events/evt_23_event_thorhall_leaves.png | Alpha | Could | F28 | No | 4 | Not started
EVT-24 | Event and weather card illustrations | Event: grapes found at Hóp | A crew member holding up a cluster of wild grapes, amazed. | Events | Illustration | 800×450 | 1 |  | res://art/events/evt_24_event_grapes_found_at_hop.png | Alpha | Should | F27 | No | 4 | Not started
EVT-25 | Event and weather card illustrations | Event: sealing | Seals hauled out on an ice floe, a hunter creeping up. | Events | Illustration | 800×450 | 1 | Only if F29 ships. | res://art/events/evt_25_event_sealing.png | Alpha | Could | F29 | No | 4 | Not started
END-01 | Ending cards and score | Ending: full win | A living camp in spring: smoke from the longhouse, cattle out to graze, a relief ship anchored, children on the shore. The best ending. | Ending | Illustration | 1920×1200 (1080 safe) | 1 | Full screen with a text panel overlay. | res://art/endings/end_01_ending_full_win.png | Beta | Must | F56 | No | 12 | Not started
END-02 | Ending cards and score | Ending: saga ending (leave rich) | Both ships deep-laden pulling away from an empty camp, the booths already sagging. Rich but leaving; scored below a living camp, never scolded. | Ending | Illustration | 1920×1080 | 1 | As above. | res://art/endings/end_02_ending_saga_ending.png | Beta | Must | F56 | No | 12 | Not started
END-03 | Ending cards and score | Ending: lost at sea | October storm, a single broken spar on a grey sea. | Ending | Illustration | 1920×1080 | 1 | As above. | res://art/endings/end_03_ending_lost_at_sea.png | Beta | Must | F56 | No | 10 | Not started
END-04 | Ending cards and score | Ending: winter starvation | A snow-buried camp, no smoke, an empty byre door open. | Ending | Illustration | 1920×1080 | 1 | As above. | res://art/endings/end_04_ending_winter_starvation.png | Beta | Must | F56 | No | 10 | Not started
END-05 | Ending cards and score | Ending: fear capped | The palisade standing, the camp abandoned in haste, both hulls gone from the shore. | Ending | Illustration | 1920×1080 | 1 | As above. | res://art/endings/end_05_ending_fear_capped.png | Beta | Must | F56 | No | 10 | Not started
END-06 | Ending cards and score | Score screen board | A large carved board for the final tally: cargo delivered, people alive in both places, goodwill left. | Score | UI frame | 1600×900 | 1 | Text drawn on top in code. | res://art/endings/end_06_score_screen_board.png | Beta | Must | F31 | No | 5 | Not started
MNU-01 | Title and menus | Title key art (layered) | The game's key image: the knarr under sail at the edge of a new coast, a single figure at the bow, a vast sky. Painted in layers (sky, far coast, sea, ship, foreground spray) for slow parallax behind the menu. | Title, Steam, itch | Layered illustration | 3840×2160 source, 1920×1080 in game | 5 layers | This one painting feeds most store art; paint it at 3840×2160. | res://art/menus/mnu_01_title_key_art.png | Beta | Must | F34 | Yes | 24 | Not started
MNU-02 | Title and menus | Logo wordmark | The title wordmark, carved or brushed letters with a restrained runic flavour, readable at small sizes. Also a stacked version and a one-colour version. | Title, Steam, itch, trailer | Logo | 1600×500 PNG + SVG | 3 versions | Transparent. Check the title for trademark clashes before final art. | res://art/menus/mnu_02_logo_wordmark.png (+ .svg) | Beta | Must | F34 | Yes | 10 | Not started
MNU-03 | Title and menus | Main menu frame | The menu panel and button column laid over the key art. | Title | UI layout | 1920×1080 | 1 | Uses the UI kit. | res://art/menus/mnu_03_main_menu_frame.png | Production | Must | F51 | No | 2 | Not started
MNU-04 | Title and menus | Options and pause backgrounds | A darkened, blurred camp view for options, and a dim overlay with a wool border for pause. | Menus | Background plate | 1920×1200 (1080 safe) | 2 |  | res://art/menus/mnu_04_options_and_pause_backgrounds.png | Production | Must | F51 | No | 3 | Not started
MNU-05 | Title and menus | Loading screen | A simple painted vignette (the star ring on a sea chest) with the spindle-whorl spinner. | Menus | Background plate | 1920×1200 (1080 safe) | 1 + spinner 8 frames |  | res://art/menus/mnu_05_loading_screen.png | Production | Should | F51 | No | 4 | Not started
MNU-06 | Title and menus | Credits background | Quiet long image of the coast at dusk for scrolling credits. | Credits | Background plate | 1920×1200 (1080 safe) | 1 |  | res://art/menus/mnu_06_credits_background.png | Polish and ship | Should | F60 | No | 3 | Not started
MNU-07 | Title and menus | Application icon | The game's icon: the star ring or the knarr's prow in a square, readable at 16 px. | Desktop, Steam client | Icon | 256×256 PNG + multi-size .ico | 1 | .ico with 16, 32, 48, 256. Godot uses icon.png. | res://art/menus/mnu_07_application_icon.png | Beta | Must | F57 | No | 3 | Not started
MNU-08 | Title and menus | Godot boot splash | A plain dark card with the wordmark, shown while the engine starts. | Boot | Background plate | 1920×1200 (1080 safe) | 1 | Set in Project Settings > Application > Boot Splash. | res://art/menus/mnu_08_godot_boot_splash.png | Beta | Must | F57 | No | 1 | Not started
VFX-01 | Particle textures | Soft particle set | Basic particle textures: soft round dot, spark, ember, droplet, foam puff, snowflake, dust mote, leaf. | All | Texture set | 64×64 each | 8 textures | White on transparent so code can tint them. | res://art/vfx/vfx_01_soft_particle_set.png | Vertical slice | Must | — | No | 2 | Not started
VFX-02 | Particle textures | Smoke puff sheet | A smoke puff that grows and fades, for chimney smoke and the fire. | Camp, Smoke rack | Sprite sheet | 256×256 per frame | 8 frames | White on transparent. | res://art/vfx/vfx_02_smoke_puff_sheet_strip.png | Vertical slice | Must | F15 | No | 2 | Not started
VFX-03 | Particle textures | Splash sheet | A small water splash, for fish, oars, and objects hitting the water. | Voyage, Fish | Sprite sheet | 256×256 per frame | 8 frames | Bottom pivot. | res://art/vfx/vfx_03_splash_sheet_strip.png | Vertical slice | Must | F05 | No | 2 | Not started
MKG-01 | Store and marketing art | Steam header capsule | Key art crop with the logo, for the top of the store page and recommendation lists. | Steam | Store art | 920×430 | 1 | Logo and artwork only (Steam rule). | marketing/mkg_01_steam_header_capsule.png | Vertical slice | Must | F61 | No | 2 | Not started
MKG-02 | Store and marketing art | Steam small capsule | Tight crop where the logo must read at tiny size; logo fills most of the space. | Steam | Store art | 462×174 | 1 | Logo and artwork only. | marketing/mkg_02_steam_small_capsule.png | Vertical slice | Must | F61 | No | 2 | Not started
MKG-03 | Store and marketing art | Steam main capsule | The big front-page capsule: key art with the logo. | Steam | Store art | 1232×706 | 1 | Logo and artwork only. | marketing/mkg_03_steam_main_capsule.png | Vertical slice | Must | F61 | No | 3 | Not started
MKG-04 | Store and marketing art | Steam vertical capsule | Portrait crop of the key art with the logo. | Steam | Store art | 748×896 | 1 | Logo and artwork only. | marketing/mkg_04_steam_vertical_capsule.png | Vertical slice | Must | F61 | No | 3 | Not started
MKG-05 | Store and marketing art | Steam page background | A subtle, dark version of the sea for behind the store page. | Steam | Store art | 1438×810 | 1 | Optional; keep it dim. | marketing/mkg_05_steam_page_background.png | Vertical slice | Should | F61 | No | 1 | Not started
MKG-06 | Store and marketing art | Steam library capsule | Portrait library tile: key art with logo. | Steam | Store art | 600×900 | 1 | Logo and artwork only. | marketing/mkg_06_steam_library_capsule.png | Beta | Must | F58 | No | 2 | Not started
MKG-07 | Store and marketing art | Steam library hero | Wide library banner of pure artwork (no logo): sky, sea, and the ship small on the left. | Steam | Store art | 3840×1240 | 1 | Artwork only; the logo sits on top. | marketing/mkg_07_steam_library_hero.png | Beta | Must | F58 | No | 3 | Not started
MKG-08 | Store and marketing art | Steam library logo | The logo alone for placing over the hero. | Steam | Store art | 1280×720 max, transparent PNG | 1 | Logo only. | marketing/mkg_08_steam_library_logo.png | Beta | Must | F58 | No | 1 | Not started
MKG-09 | Store and marketing art | Steam library header | Library header capsule, same layout as the store header. | Steam | Store art | 920×430 | 1 | Logo and artwork only. | marketing/mkg_09_steam_library_header.png | Beta | Must | F58 | No | 1 | Not started
MKG-10 | Store and marketing art | Steam client and community icons | Client shortcut icon and the small community icon. | Steam | Store art | 256×256 PNG/ICO, 184×184 JPG | 2 | From the application icon. | marketing/mkg_10_steam_client_and_community_icons.png | Beta | Must | F58 | No | 1 | Not started
MKG-11 | Store and marketing art | Steam event cover and header | Templates for news posts: a cover image (marketing text allowed) and a wide header. | Steam | Store art | 800×450, 1920×622 | 2 templates | Reusable for updates and Next Fest. | marketing/mkg_11_steam_event_cover_and_header.png | Alpha | Should | F61 | No | 2 | Not started
MKG-12 | Store and marketing art | Screenshots | At least five in-game screenshots: a fix in fog, a camp in summer, the market, winter, and timber leaving the slip. Captured from the game, then cropped and staged. | Steam, itch, press | Screenshot | 1920×1080 minimum | 5–10 | Claude can add a clean screenshot mode (no HUD) to the build. | marketing/mkg_12_screenshots.png | Beta | Must | F34 | No | 4 | Not started
MKG-13 | Store and marketing art | itch.io cover image | Cover for the itch.io page and listings: key art crop with the logo. | itch.io | Store art | 630×500 | 1 | Max 3840×2160, 3 MB. | marketing/mkg_13_itch_io_cover_image.png | Vertical slice | Must | F61 | No | 1 | Not started
MKG-14 | Store and marketing art | itch.io banner and page background | A wide banner with the logo for the top of the itch page, and a dim sea texture for the page background. | itch.io | Store art | 960×300, 1920×1080 | 2 | Banner shows up to 960 px wide. | marketing/mkg_14_itch_io_banner_and_page_background.png | Vertical slice | Should | F61 | No | 2 | Not started
MKG-15 | Store and marketing art | Trailer end card and title cards | End card with the logo, store buttons area, and release date; three short title cards for the trailer beats (Navigate, Settle, Return). | Trailer | Video still | 1920×1080 | 4 cards | Leave space for platform logos added later. | marketing/mkg_15_trailer_end_card_and_title_cards.png | Polish and ship | Must | F34 | No | 4 | Not started
MKG-16 | Store and marketing art | Press kit logo set | Logo on dark, on light, and transparent; plus the key art without text. | Press | Logo | 3840×2160 max | 4 files |  | res://art/marketing/mkg_16_press_kit_logo_set.png (+ .svg) | Polish and ship | Should | F34 | No | 1 | Not started
Total estimated hours | [13 empty] | 1327